## S.E. Log Pg 1
SOIL EROSION PLANS
| NUMBER | DATE REC'D | SENT TO ENGINEER | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments | ***********************
Barber Creek Corp. Park
Barber Creek Drive | 2328 | 2001-02-08 | 2001-02-09 | 2001-02-13 | 2001-02-27 | 2001-04-02 | 2001-04-05 | 2001-10-04
Prince Ave. Baptist Church | [8 empty] | Grading only
Ruth Jackson & 78 | 2352 | 2001-03-13 | 2001-03-13 | 2001-03-26 | 2001-04-05 | 2001-04-20 | 2001-04-25 | 2001-04-27 | released 8/6
Dr. Lawrence George - Dentist
Jennings Mill Road | 381 | 2001-04-03 | 2001-04-04 |  | 2001-04-05 |  | 2001-04-16 | 2001-04-17
Oconee Connector-Barber Creek
Sewer Extension | N/A | 2001-04-04 | 2001-04-04 |  | 2001-04-05 |  | 2001-04-26 | 2001-04-30
The Village @ Dove Creek
Dove Creek Road | 382 | 2001-04-06 | 2001-04-20 | 2001-04-23 | 2001-04-24 | 2001-04-26 | 2001-05-11 | 2001-05-17
Old Waverly Phase 2
Rocky Branch Road | 385 | 2001-04-11 | 2001-04-11 |  | 2001-04-12 |  | 2001-04-17 | 2001-04-18
Faith Presbyterian Church Parking Lot
2191 Mars Hill Road | 389 | 2001-04-18 | 2001-04-25 |  | 2001-04-26 |  | 2001-05-02 | 2001-05-04
John Robinson (Farm Pond)
Twin Oaks Trail | 390 | 2001-04-18 |  |  | 2001-04-18 | 2001-04-19 | 2001-05-02 | 2001-05-04
Georgian Oaks Estates
Saxon Road | 2372 | 2001-05-14 | 2001-05-15 |  | 2001-05-17 |  | 2001-05-22 | 2001-05-23
Watk. First UMC (Parking)
1331 New High Shoals Road | 2391 | 2001-05-25 | 2001-05-29 |  | 2001-06-01 | 2001-06-18 | 2001-08-02 | 2001-08-03
78-316 Sewer Collection System
U.S. 78 & 316 | 2393 | 2001-06-01 | 2001-06-04 |  | 2001-06-08 | 2001-06-18 | 2001-06-26 | 2001-06-28
Walmart | [8 empty] | Clearing
| 1001 | 2001-06-07 | 2001-06-11 |  | 2001-06-12 | 2001-06-18 | 2001-07-25 | 2001-07-26 | Grubbing
2260 Mars Hill Road Office
2260 Mars Hill Road | 1002 | 2001-07-12 | 2001-07-16 |  | 7/19/010 | 2001-07-25 | 2001-08-02 | 2001-08-03
Silverleaf Phase II
Jimmy Daniel Road | 1003 | 2001-07-24 | 2001-07-25 |  | 2001-07-30 | 2001-08-02 | 2001-08-08 | 2001-08-09
Mars Hill Business Park
Mars Hill Road | 1004 | 2001-08-03 | 2001-08-03 | 2001-08-16 |  | 2001-12-07 | 2001-12-13 | 2002-01-09
Founders Grove Phase III
Founders Grove | 1005 | 2001-08-10 | 2001-08-16 |  | 2001-08-21 |  | 2001-08-22 | 2001-08-23

## S.E. Log Pg 2
| NUMBER | DATE REC'D | SENT TO ENGINEER | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
McDonalds @ Jennings Mill
Epps Bridge Pkwy | 1006 | 2001-09-04 | 2001-09-04 |  | 2001-10-03 |  | 2001-10-09 | 2002-08-01
Belmont Place
53 Near 78 | 1007 | 2001-09-05 |  |  | 2001-09-17 | 2001-09-24 | 2001-10-09 | 2001-10-16 |  | 9/01 TO 3/02
Hebron Christian Church
Hebron Church Road | N/A | 2001-09-10 |  |  | 2001-10-24 |  | 2001-10-29 | 2001-10-31
Oaklake Subdivison |  |  |  | J. Holland P/Up
Mars Hill Road | 1008 | 2001-10-05 |  | 2002-01-23
Morrison Street Business Park
Morrison Street | 1009 | 2001-10-23 | 2001-10-23 |  | 2001-11-07 |  | 2001-11-16 | 2001-11-19
Southwind Manor
Union Church Road | 1010 | 2001-10-25 | 2001-10-25 |  | 2001-10-30 |  | 2001-11-05 | 2002-01-22
Oconee Baptist Church
| 1011 | 2001-12-10 |  |  |  | 2002-01-11 | 2002-04-02
Trail Top Distribution, LLC
Industrial Blvd. | 1012 | 2001-12-20 |  |  | 2001-12-26 | 2002-12-28 | 2002-01-09 | 2002-01-10
New Oconee County High School
Hog Mountain Road | 1013 | 2002-01-04 | 2002-01-07 |  | 2002-01-09 | 2002-01-11 | 2002-01-29 | 2002-02-07
Phinizy Meadows
Welbrook Road | 1014 | 2002-01-17 | 2002-01-22 |  | 2002-01-24 |  | 2002-02-05 | 2002-03-29
Epps Bridge Square
Epps Bridge Road & Dowdy Road | 1015 | 1902-10-11 | 2002-01-22 |  | 2002-01-24 |  | 2002-02-05 | 2002-03-04
San. Swr Lift Sta & Forcemain New High Sch
Rocky Branch Rd & Hog Mtn Rd. | 1016 | 2002-02-06 | 2002-02-07 |  | 2002-04-22 |  | 2002-04-24
Sterling Mills Phase II
Rocky Branch Road | 1017 | 2002-02-07 | 2002-02-07 |  | 2002-02-12 |  | 2002-02-13 | 2002-04-29
S.R. 53/Rocky Branch Rd Widening/Int. Imp.
S.R. 53 & Rocky Branch Road | 1018 | 2002-02-07 | 2002-02-07 |  | 2002-02-12 | 2002-02-14
University Parkway
Daniells Bridge Road | 1019 | 2002-02-07 | 2002-02-07 |  | 2002-02-07 | 2002-02-20 | 2002-03-06
Oaklake Subdivision | [7 empty] | Clear/Grub Only
Mars Hill Road | 1020 | 2002-02-08 |  |  | 2002-02-28 |  | 2002-03-05 | 2002-03-13
Oconee Industrial Park Lots 1AA-1AE
1181 Greensboro Hwy | 1023 | 2002-03-06 | 2002-03-07 |  | 2002-03-12 |  | 2002-03-15
Baker Business Park
Mars Hill Road | 1024 | 2002-03-06 | 2002-03-07 |  | 2002-03-12 |  | 2002-03-15
Boulder Springs Phase II | 1025
New High Shoals Road (C & G Only) | 1026 | 2002-03-11 | 2002-03-12 |  | 2002-03-13 |  | 2002-03-15
Summer Hill Recreation Club
Daniell's Bridge/Chestnut Hill Road | 1027 | 2002-03-15 | 2002-03-15 |  | 2002-03-19 |  | 2002-03-28 | 2002-07-03

## S.E. Log Pg 3
| NUMBER | DATE REC'D | SENT TO ENGINEER | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Cracker Barrel
Epps Bridge Pkwy | 1029 | 2002-03-15 | 2002-03-15 |  | 2002-03-19 | 2002-03-28 | 2002-04-12 | 2002-04-15
Christian Lake
Harden Hill Road & VFW Drive | 1028 | 2002-03-20 | 2002-03-20 |  | 2002-03-20 | 2002-03-28 | 2002-04-02 | 2002-04-05
Rolling Glen
High Shoals Road | 1032 | 2002-04-04 | 2002-04-05 |  | 2002-04-09 | 2002-04-17 | 2002-04-24 | 2002-06-24
Chambers Ct. Blk "O" & "P"
Meriweather Drive | 1033 | 2002-04-04 | 2002-04-05 |  | 2002-04-09 | 2002-04-12 | 2002-04-24 | 2002-05-07
JMCC Tennis Courts Imp/Add
1101 Mill Pond Court | 1034 | 2002-04-04 | 2002-04-05 |  | 2002-04-09 | 2002-04-17 | 2002-05-08
Franklin Grove Driving Range
3001 Monroe Highway | 1035 | 2002-04-22 |  |  | 2002-04-24 |  | 2002-05-08 | 2002-05-09
Lane Creek Amenity Lot
Lane Creek Drive | 1036 | 2002-05-07 | 2002-05-08 |  | 2002-05-21 |  | 2002-05-23
Athens Area Association of Realtors
Meriweather Drive | 1037 | 2002-05-07 | 2002-05-08 |  | 2002-05-21 |  | 2002-05-23 | 2002-07-03
Founders Executive Park
1040 Founders Blvd | 1038 | 2002-05-13 | 2002-05-14 |  | 2002-05-21 |  | 2002-05-23 | 2002-07-03
Colony Square
Hwy 53 | 1039 | 2002-05-20 | 2002-05-21 |  | 2002-05-22 |  | 2002-05-23
Jeffery's Walk
New High Shoals Road | 1041 | 2002-06-25 | 2002-06-26 |  | 2002-07-02 |  | 2002-07-19
Twin Ponds Office Park
1150 Julian Drive | 1042 | 2002-07-08 | 2002-07-09 |  | 2002-07-25 |  | 2002-08-19
Belfair Subdivision
Pete Dickens Road | 1043 | 2002-07-15 | 2002-07-16 |  | 2002-07-25 |  | 2002-07-29
Thronwood | [8 empty] | Released
New High Shoals Road | 1044 | 2002-07-15 | 2002-07-16 |  | 2002-07-25 |  | 2002-07-29 | 2002-08-02 | C & G Only
Jennings Mill Golf Club House
Chambers Court | 1045 | 2002-07-25 | 2002-07-26 |  | 2002-08-07 |  | 2002-08-19
Faith Presbyterian Church
2191 Mars Hill Road | 1046 | 2002-08-13 |  |  | 2002-09-18 | 2002-08-26 | 2002-09-17
St. Philothea Greek Church
| 1049 | 2002-09-10 | 2002-09-11 |  | 2002-09-18 |  | 2002-10-02
Lampkin Branch Business Park
2181 Veterans Memorial Pkwy | 1050 | 2002-09-11 | 2002-09-11 |  | 2002-09-18 |  | 2002-10-02

## S.E. Log Pg. 4
| NUMBER | DATE REC'D | SENT TO ENGINEER | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Founders Grove Office Lot 59/60
1091/1071 Founders Blvd | 1052 | 2002-09-19 |  |  | 2002-10-04 | 2002-10-15
Ivywood South Block "I"
Robinson Court | 1053 | 2002-09-26 |  |  | 2002-10-25 | 2002-11-08
New High School
| 1054 | 2002-09-20 |  |  | 2002-10-04 | 2002-10-15 | 2002-10-25 | 2002-11-04
SR 53 Water Main Ext.
Hwy 53 | 1055 | 2002-10-03 |  |  | 2002-10-04
Southern School Services
Oconee Industrial Blvd | 1056 | 2002-10-25 |  |  | 2002-10-28 |  | 2002-11-08 | 2002-11-12
Dickens Corner
Hwy 78 & Pete Dickens Road | 1058 | 2002-12-02 | 2002-12-03 |  | 2002-12-19 |  | 2002-12-20
Daniels Bridge Sewer Project
Daniells Bridge Road | 1059 | 2002-12-12 | 2002-12-12 |  | 2002-12-19 | 2002-12-24 | 2003-01-09 | 2003-01-17
J.D.'s Kitchen & Bath
7551 Macon Highway | 1062 | 2003-01-06 |  |  | 2003-01-07
Athletic Club for Karate - Borders
1011 Tower Place | 1063 | 2003-02-07 |  |  | 2003-02-08
Double J
Jones Road | 1064 | 2003-02-27 |  |  | 2003-02-28 | 2003-03-07 | 2003-04-03 | 2003-04-11
Evanridge (Busienss S/D) | [8 empty] | C & G Only
Hog Mountain Road | 1065 | 2003-03-06 |  |  | 2003-03-24 | 2003-03-27 | 2003-04-10 | 2003-09-23 | 2003-04-21
Oconee Presbyterian
2601 Hog Mountain Road | 1066 | 2003-03-07 |  |  | 2003-03-11 | 2003-03-20
Boulder Springs Amenity Lot
| 1067 | 2003-03-21 |  |  | 2003-03-24 | 2003-03-27 |  | 2003-05-28
Boulder Spirngs Phase II
New High Shoals Road | 1068 | 4/70/3 |  |  | 2003-04-08 |  | 2003-04-14 | 2003-09-17
Mulberry Plantation
Union Church Road | 1069 | 2003-04-07 |  |  | 2003-04-08 |  | 2003-04-15 | 2003-05-20
Timarron
Hodges Mill Road | 1070 | 2003-04-07 |  |  | 2003-04-08 |  |  | 2003-06-06
Taylors Iron Co. Inc.
Industrial Drive | 1071 | 2003-04-23 |  |  | 2003-04-24 |  | 2003-05-05 | 2003-05-06
Bridlegate
3010 Astondale Road | 1074 | 2003-05-29 |  |  | 2003-05-30 |  | 2003-06-10 | 2003-07-25

## S.E. LOG Pg. 5
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Wingate Hotel
1241 Old Epps Bridge Road | 1075 | 2003-09-23 |  | 2003-09-23 | 2003-10-03 | 2003-11-13 | 2003-12-09
Zaxby's Rest.
1800 Epps Bridge Pkwy | 1076 | 2003-06-02 |  | 2003-06-06 |  | 2003-06-10 | 2003-08-25
Lot 3 The Pointe @ Epps Bridge
Epps Bridge & Dowdy Road | 1078 | 2003-06-12
Athens Academy Arts & Science Bldg
2181 Spartan Lane | 1079 | 2003-06-20 |  | 2003-06-24 |  | 2003-07-07 | 2003-07-15
Daniells Bridge Technology Center |  |  |  |  | 2003-08-25
Daniells Bridge Road | 1081 | 2003-07-03 |  |  | 2003-08-11 |  | 2003-09-05
Clotfelter Road Water Main
Clotfelter Road | 1082 | 2003-07-07 |  |  |  |  | 2003-08-01
Willowynd
Norton Road | 1083 | 2003-07-28 |  |  | 2003-08-15 | 2003-08-22 | 2003-09-02
Woodruff Estates
Saxon Road | 1084 | 2003-07-31 |  | 2003-08-18 | 2003-08-25 | 2003-09-15 | 2003-10-06
Bank of America
Epps Bridge Road/Dowdy Road | 1085 | 2003-08-15 |  | 2003-08-18 | 2003-08-25 | 2003-09-02 | 2003-09-05
Meadow Brooke
1610 Norton Road | 1086 | 2003-08-18 |  | 2003-08-18 |  | 2003-08-22 | 2003-09-05
Athens Academy Arts & Science
Spartan Lane | 1087 | 2003-08-18 |  | 2003-08-18 |  | 2003-08-22 | 2003-09-30
Sims Crossing
8260 Hog Mountain Road | 1088 | 2003-08-22 |  |  |  | 2003-09-02 | 2003-09-08
The Georgia Club
Barber Creek Drive | 1089 | 2003-08-26 |  |  |  | 2003-09-02 | 2003-09-05
Creekside
Jimmy Daniel Road | 1090 | 2003-08-29 |  |  |  | 2003-09-23 | 2003-10-30
Watkinsville First Baptist
Simonton Bridge Road | 1091 | 2003-08-29 |  |  |  | 2003-09-05 | 2003-09-23
Thornwood Properties
New High Shoals Road | 1092 | 2003-09-04 |  |  |  | 2003-09-15
Piedmont Glen
Clotfelter Road/Hwy 53 | 1098 | 2003-09-29 |  | 2003-09-29 |  | 2003-10-14 | 2004-04-05
Pembrook Estates
McRee Mill Road | 1099 | 2003-10-01 |  | 2003-10-06 |  | 2003-10-14 | 2003-10-30
Magnolia Estates
Virgil Langford Road | 1100 | 2003-10-03 |  | 2003-10-06 |  |  | 2003-11-26
Colony Square Lot 2
Jamestown Boulevard | 1101 | 2003-10-07 |  |  |  | 2003-10-14 | 2003-10-30

## S.E. LOG Pg. 6
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Moss Creek
Cliff Dawson Road | 1102 | 2003-10-08 |  |  |  | 2003-11-07 | 2004-01-03
Waffle House
U.S. Hwy 441 | 1103 | 2003-10-08 |  |  |  | 2003-11-07 | 2004-01-03
Hickory Hills/Sherwood Forest Wtr Main
Simonton Bridge Road | 1105 | 2003-10-22 |  |  |  | 2003-11-07 | 2003-11-13
Christian Lake Phase 2
Harden Hill Road | 1106 | 2003-11-13 |  |  |  | 2003-11-24 | 2003-11-26
Grace Baptist Church Classrooms
6401 Hog Mountain Road | 1107 | 2003-11-17 |  |  |  | 2003-11-24 | 2004-04-27
Lot 20 Mars Hill Business Park
Mars Hill Road | 1108 | 2003-11-19 |  |  |  | 2003-11-24 | 2004-01-12
Barber Creek Corp. Park Phse 2
Barber Creek Drive | 1109 | 2003-11-20 |  |  | 2003-12-05 | 2003-12-15 | 2003-12-18
Sunrise Meadows
2340 Hebron Church Road | 1110 | 2003-11-25 |  |  |  | 2003-12-05
Brookshire
Rocky Branch Road | 1111 | 2003-11-25 |  |  |  | 2003-12-05
Watkinsville Church of Christ
2001 Ray's Church Road | 1112 | 2003-11-25 |  |  |  | 2003-12-05 | 2004-01-12
Town Center
441/Barnett Shoals Road | 1113 | 2003-12-04 |  |  | 2003-12-15 | 2004-01-16 | 2004-01-27
McRees Mill Wtr Main Extension
Mcree Mill Road | 1114 | 2003-12-09 |  |  |  | 2003-12-15 | 2004-01-05
Morningside
Hodges Mill Road | 1115 | 2003-12-23 |  |  | 2004-01-14 | 2004-01-28 | 2004-04-05
All Sports Training | [7 empty] | C & G
1031 Julian Drive | 1117 | 2004-01-27 |  |  |  | 2004-02-05 | 2004-04-02 | 2004-02-13
Brookhaven
Hodges Mill Road | 1118 | 2004-02-02 |  |  |  | 2004-02-17 | 2004-04-19
Pecan Bluff
Thrasher Drive | 1119 | 2004-02-05 |  |  | 2004-02-18 | 2004-02-25 | 2004-03-03
Ryan's |  | 2004-03-08
Dowdy Rd/Epps Bridge Pkwy | 1120 | 2004-02-05 | 2004-02-10
Peatmoss Park | [7 empty] | C & G
Pete Dickens Road | 1121 | 2004-02-11 |  |  |  | 2004-02-25 | 2004-04-06 | 2004-03-04
Camden Park
Simonton Bridge Road | 1122 | 2004-01-16 |  |  | 2004-03-04
Rowan Oak |  |  |  |  | 2004-03-12 |  |  | C & G
Rocky Branch Road | 1123 | 2004-01-17 |  |  | 2004-03-04 | 2004-03-16 | 2004-03-25 | 2004-03-17
Summit @ Mars Hill |  |  |  |  | 2004-03-12 |  |  | C & G 3/17/04
Mars Hill Road | 1124 | 2004-02-24 |  |  | 2004-03-05 | 2004-03-16 | 2004-03-25
Dartmouth Phase I |  |  |  |  | 2004-03-12
Lenru Road | 1127 | 2004-03-01 |  | 2004-03-03 | 2004-03-04 | 2004-03-26 | 2004-04-26
Franklin Grove
Monroe Highway | 1128 | 2004-03-01 |  | 2004-03-03 | 2004-03-05
Creekside Phase 2
Jimmy Daniel Road | 1129 | 2004-03-01 |  | 2004-03-03

## S.E. LOG Pg. 7
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Peatmoss Park (Revision) | [7 empty] | C & G
Pete Dickens Road | 1130 | 2004-03-08 |  |  | 2004-03-15 | 2004-03-19 | 2004-04-06 | 2004-03-23
Mars Hill Baptist Annex |  |  |  |  | 2004-05-12
2661 Mars Hill Road | 1134 | 2004-03-29 |  |  | 2004-04-15 | 2004-05-19 | 2004-06-02
Bethabara Baptist Chruch Expansion
4651 Monroe Highway | 1135 | 2004-04-05 |  |  | 2004-05-12
Boulders Springs Phase 3 (C & G)
New High Shoals Road | 1136 | 2004-04-05
Meadow Springs |  |  |  |  | 2004-05-12
Cliff Dawson Road | 1138 | 2004-04-05 |  |  | 2004-04-15
New Office Bldg - Stonebridge Bus. |  |  |  |  | 2004-06-24
1101 Park Drive | 1141 | 2004-04-13 |  |  | 2004-04-26
Bell Ridge
Mars Hill Road | 1142 | 2004-04-20
Copperville |  |  |  |  | 2004-05-27
Union Church Road | 1147 | 2004-05-03 |  |  | 2004-05-19 | 2004-06-02 | 2004-06-01
Wisteria Ridge
75 N Main Street (Inside City Limits) | 1151 | 2004-06-01 |  |  |  | 2004-06-17 | 2004-06-24
Peatmoss Park Force Main
Pete Dickens Road | 1154 | 2004-06-22
Sommerset
Clotfelter Road | 1148 | 2004-06-04 |  |  | 2004-06-24
Prince Ave. Christian School
Ruth Jackson Road | 187 | 2004-07-01
Apalachee Downs(Ridgeway Farms)
Ridgeway Road | 254 | 2004-07-07 |  |  |  | 2004-07-15
The Market @ Epps Bridge | [5 empty] | C & G Only
Jennings Mill/Epps Bridge | 293 | 2004-07-09 |  |  |  | 2004-07-15 | 2004-07-26
The Village @ Manders Crossing
1260 Mars Hill Road | 198 | 2004-07-02 |  |  |  | 2004-07-15
RRA Office Development
1741 Hog Mountain Road | 451 | 2004-07-23
David & Neva Townsend
2051 Elder Mll Road | 470 | 2004-07-26
Fire Mountain Restaurant
Dowdy Rd/Epps Bridge Rd |  | 2004-07-27
Epps Bridge Rd & Daniels Bridge Rd
Pump Station Replacement | E04-211 | 2004-08-13
Jennings Mill Executive Suites
1361 Jennings Mill Road | 528 | 2004-07-30 |  |  | 2004-08-11 | 2004-08-18 | 2004-09-01

## S.E. Log Pg. 8
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Windridge Office Park
Mars Hill Road | 914 | 2004-09-03 |  |  |  | 2004-09-13 | 2004-10-26
The Market @ Epps Bridge (Addition) | [6 empty] | C & G Only
Epps Bridge Pkwy | 921 | 2004-09-08 |  |  |  | 2004-09-29 | 2004-09-30
Kohls Shopping Center |  | C & G Only |  |  |  |  | C & G Only
Epps Bridge Parkway | 1065 | 2004-09-22 |  |  |  | 2004-09-24 | 2004-09-30
Evanridge (Amended)
Ga Hwy 53 | 1216 | 2004-10-07 |  |  | 2004-10-15 | 2004-11-10 | 2004-11-19
Carolina's Place
3131 Hog Mountain Road | 1312 | 2004-10-19 |  |  |  | 2004-11-02 | 2004-12-14
David Townsend
2051 Elder Mill Road | 1362 | 2004-10-25 |  |  | 2004-11-02 | 2004-11-12 | 2004-11-16
Next Generation Day Care
1181 Rocky Branch Road | 1339 | 2004-10-21 |  |  | 2004-11-02 | 2004-11-12 | 2004-11-16
Parkway Shops @ Epps Bridge
Epps Bridge Parkway | N/A | 2004-10-21 |  |  |  | 2004-11-02 | 2004-11-05
Boulder Springs Phase 3 |  |  |  |  | 2004-11-22
2771 New High Shoals Road | 1475 | 2004-11-03 |  |  | 2004-11-12 | 2004-12-20
Mark H. Anthony
1060 Jimmy Daniel Road | 1543 | 2004-11-09 |  |  |  | 2004-11-22 | 2004-11-22
M & P Grading
1100 & 1120 Industrial Drive | 1594 | 2004-11-17 |  |  | 2004-11-29 | 2004-12-20 | 2004-12-23
Townside
5391 Price Mill Road | 1879 | 2004-12-23 |  |  | 2005-01-24
Westland MPD
78 @ Goat Farm Road | 2161 | 2005-01-11 |  |  | 2005-01-24
New Park for Oconee Parks & Rec
Hwy. 53 | N/A | 2005-01-06 |  |  | 2005-01-24
Rambling Rill
1411 Sikes Road | 2607 | 2005-02-01 |  |  |  | 2005-02-11 | 2005-03-09
The Estates @ Cole Springs
Cole Springs Road | 2659 | 2005-02-04 |  |  |  | 2005-02-25 | 2005-03-11
Dickens Corner - FM & Sanitary Swr |  |  | on hold
Hwy 78 & Pete Dickens Road | 2473 | 2005-01-25
Westland - Force Main Ext |  |  | on hold
hwy 78 & Goat Farm Road | 2473 | 2005-01-25
Ryland Hills (C & G)
1321 McRees Mill RD | 2715 | 2005-02-08 |  |  | 2005-02-15
San. Sewer & FM for Hwy 78 | Resubmitted | 2006-06-23
Hwy 78 | 2707 | 2005-02-08 |  |  | 2005-02-15 | 2006-08-21 | 2006-08-24

## S.E. Log Pg 9
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Williams Down
Hwy 441 - Farmington | 2825 | 2005-02-15 |  |  |  |  | 2005-04-09
Triple Creek @ Malcom Bridge Phse 2
Lenru Road | 2887 | 2005-02-18 |  |  | 2005-03-04 |  | 2005-10-18
Whitlow Creek Estates
Union Church @ High Shoals | 2932 | 2005-02-22 |  | 2005-02-22 | 2005-02-25 |  | 2005-05-03
Moores Ford/Ridgeway Wtrline Ext
Morores Ford / Ridgeway Road |  | 2005-02-11 |  | 2005-02-16 | 2005-02-25
The Market @ Epps Bridge
1221 Old Epps Bridge Road |  | 2005-03-07 |  | 2005-03-09 | 2005-03-11
Jimmy Daniel Road Site
1681 Jimmy Daniel Road | 3259 | 2005-03-11 |  |  | 2005-03-25
Barber Creek Corp Park Phase 3
1050 Barber Creek Drive | 3335 | 2005-03-15
Hampton Valley Business Park
2881 Monroe Hwy | 3341 | 2005-03-15 |  |  | 2005-03-25 |  | 2005-05-10
Lane Creek Plantation Phase III (C&G)
Lane Creek Drive | 3312 | 2005-03-16 |  |  | 2005-03-25 | 2005-04-01 | 2005-04-06
Lane Creek Plantation Phase III
Lane Creek Drive |  | 2005-04-01 |  |  | 2005-04-22 |  | 2005-06-06
Ryland Hills
McRee's Mill Road | 3749 | 2005-04-05 |  |  | 2005-04-18 | 2005-04-22 | 2005-05-10
Coldwater Creek |  |  |  |  | 2005-04-18
Whippoorwill Road |  | 2005-04-07 |  |  | 2005-04-22 |  | 2005-06-06
Fast Phil's
3351 Macon Hwy | 3853 | 2005-04-12
Dials Mill Road Water Main
Dials Mill Road |  | 2005-03-18 |  |  | 2005-04-22 |  | 2005-05-05
Woodridge North Office Park
1011 Woodridge Lane | 4071 | 2005-04-26
Oconee County New Park
Hog Mountain Road |  | 2005-05-04
Lakewood Manor
2151 Macon Hwy (Kevin Hall) | 4237 | 2005-05-10 |  |  | 2005-05-12 | 2005-05-31 | 2005-06-06
The Avenue @ Butler's Crossing |  |  |  |  | 2005-06-10
Ga Hwy 53 | 4312 | 2005-05-16 |  |  | 2005-05-24 | 2005-06-17 | 2005-06-28
LAD Truck Lines
Barnett Shoals Road | 4323 | 2005-05-17 |  |  | 2005-05-24 |  | 2005-06-03
Lot 18 & 19 Mars Hill Business Park
Commerce Court | 4370 | 2005-05-20 |  |  |  | 2005-05-31 | 2005-07-18

## S.E. Log Pg 10
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Williams Downs Amended
Ga Hwy 441, Farmington Ga |  | 2005-05-25 |  |  |  | 2005-05-31 | 2005-06-08
Colony Square Plaza
1021 Jamestown Blvd | 4467 | 2005-05-31 |  |  |  | 2005-06-10 | 2005-08-02 |  | 5/05 TO 10/05
Willow Creek
3231 Hog Mountain Road | 4472 | 2005-05-31 |  |  | 2005-06-10
Whitlow Creek (Amended)
|  | 2005-05-31 |  |  | 2005-06-10
The Exchange @ Daniells Bridge |  |  |  |  | 2005-06-24
2390 Daniells Bridge Road | 4503 | 2005-06-02 |  |  | 2005-06-10 | 2005-07-01 | 2005-07-06
Legacy Academy Daycare |  |  |  |  | 2005-06-24 |  |  | p/u
Daniells Bridge Road | 4538 | 2005-06-06 |  |  | 2005-06-10 | 2005-07-01 | 2005-07-06 | 2005-08-09
Saddle Ridge
New High Shoals Road | 4807 | 2005-07-11 |  | 2005-07-13 | 2005-07-19 | 7/220/5
Parkside Phase 1 (C & G Only)
Hog Mtn Rd & Mars Hill | 4833 | 2005-07-14 |  | 2005-07-14
Oconee Youth Playhouse
1070 Jamestown Blvd | 4841 | 2005-07-15 |  |  |  | 2005-07-29
University Pkwy Office & Tech Park 2
Daniells Bridge Road | 4926 | 2005-07-26 |  |  | 2005-07-29 | 2006-06-30 | 2006-07-11
PMFM Financial
1061 Cliff Dawson Road | 4959
Rivers Edge
2250 Moores Ford Road | 4974 |  |  | 2005-08-04 | 2005-08-19 |  | 2005-10-17
Garrett Road |  |  |  |  | 2005-09-09
1351 Garrett Road | 5078 | 2005-08-18 |  | 2005-08-19 | 2005-08-29
St. Marys Hospice Facility
Jennings Mill Road | 5009 | 2005-08-09 |  | 2005-08-09 | 2005-08-12 | 2005-11-09 | 2005-11-15
LAD Trucking Phase II
Barnett Shoals Road | 5167 | 2005-08-30
OC Jail & E911/EOC
1100 Exp. Station Road |  | 2005-08-22 |  |  |  | 2005-08-29 | 2005-08-31
Thornwood SS Ext.
Hwy 441 & New High Shoals Rd | 5478 | 2005-10-10 |  | 2005-10-10 |  | 2005-11-04 | 2005-11-08
Copperville Lift Station Modification
Copperville Subd. | 5503 | 2005-10-12 |  | 2005-10-12 |  | 2005-11-04 | 2005-11-08
Oconee Springs @ The Ga Club
Barber Creek Road | 5528 | 2005-10-14 |  | 2005-11-11 | 2005-11-18 | 2005-12-02 | 2005-12-06 | C & G Only
Oconee Heritage Park
2543 Macon Hwy | N/A | 2005-10-20 |  |  | 2005-11-04

## S.E. Log Pg 11
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Church of the Nations |  |  |  |  | 2006-01-20
8780 N. Macon Hwy. | 5629 | 2005-10-31 |  | 2005-10-31 | 11/9-12/23/05 | 2006-02-03 | 2006-02-16
New Park Revisions
Hwy 53 |  | 2005-05-04 |  | 2005-11-07 | 2005-11-18 | 2005-12-09 | 2005-12-29
Butler's Crossing Center (Shopping)
2120 Hog Mountain Road | 5593 | 2005-10-26 |  | 2005-10-31 |  | 2005-11-09 | 2005-11-15
Lenru Park Office Development | [8 empty] | 10/05 to 2/06
1561 Lenru Road | 5788 | 2005-11-22 |  |  |  | 2005-12-02 | 2006-01-11
Grace Fellowship |  |  |  |  | 2005-12-02
1120 Malcom Bridge Road | 5664 | 2005-10-24 |  | 2005-11-07 | 2005-11-18 | 2005-12-09 | 2005-12-29
The Summit @ Mars Hill Phse 2
3651 Mars Hill Road | 5855 | 2005-12-05 |  |  |  | 2005-12-16 | 2006-02-01
Grove Park
Hwy 53/Hog Mtn Rd | 5738 | 2005-11-15 |  |  | 2005-11-28 | 2005-12-02 | 2006-05-22
Lee Ridge | [5 empty] | 2006-01-26
Flat Rock Road | 5907 | 2005-12-13 |  |  |  | 2005-12-16 | 2006-03-10
The Village @ Malcolm Bridge
Malcom Bridge & Lenru Road | 5953 | 2005-12-21 |  |  | 2006-01-10 | 2006-03-03 | 2006-06-12
Barnett Shoals Rd Private Drive
2231 Barnett Shoals Road | 5957 | 2005-12-21 |  |  |  | 2006-01-20 | 2006-01-26
Pebble Creek S/D | [7 empty] | C & G Only
Greensboro Hwy/Ga Hwy 15 |  | 2005-12-21 |  |  |  | 2006-01-27 | 2006-04-24 | 2006-02-14
Creekside Country Club
4080 Barnett Shoals Road | 6219 | 2006-01-10 |  |  | 2006-01-17 | 2006-02-24 | 2006-03-09
Mars Hill Business Park Lot 21
1060 Commerce Drive (ABE Cons.) | 6288 | 2006-01-12 |  |  |  | 2006-01-20 | 2006-02-13
Fast Phils Convenience Store
2000 Atlanta Hwy | 6454 | 2006-01-24 |  |  | 2006-02-03
Westland Phase 2
Goat Farm Road | 6603 | 2006-01-31 |  |  |  | 2006-02-15 | 2006-02-23
441 Commercial Development | [7 empty] | On hold
7551 Macon Hwy | 6765 | 2006-02-09 | [5 empty] | per owner
Somerset Amenity Area
1148 Wade Drive | 6795 | 2006-02-14 |  |  |  | 2006-03-03 | 2006-03-16
Get in the Swim
1545 Bishop Farms Pkwy South | 6796 | 2006-02-14 |  |  |  | 2006-02-16 | 2006-03-22
Meridian Amenity Area
1709 Syndney's Pass | 6802 | 2006-02-14 |  |  |  | 2006-02-24 | 2006-03-17
Oconee Meadows Office Park
2410 Hog Mountain Road | 6853 | 2006-02-17 |  |  | 2006-02-24 | 2006-03-31 | 2006-07-28

## S.E. Log Pg 12
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Birchmore Hills Wtrline Replacement
Daniells Bridge Road |  | 2006-02-28 |  |  |  | 2006-03-03 | 2006-04-11
RKR Medical Arts Develop.
1023 Dowdy Road | 7137 | 2006-03-10 |  |  |  | 2006-03-24 | 2006-05-01
Parkside Phase 1
Hog Mtn & Mars Hill Rd | 7175 | 2006-03-14 |  |  |  | 2006-04-28 | 2006-05-11
The Ga Club - Oconee Springs
Barber Creek | N/A | 2006-03-21 |  |  |  | 2006-03-31 | 2006-04-17
Pebble Creek Phse 2 (C & G Only) | [8 empty] | 2/06 to 5/06
Greensboro Hwy/Hwy 15 | 7335 | 2006-03-22 |  |  |  | 2006-04-07 | 2006-04-11
Parkside Phase II (C & G Only)
Hog Mtn & Mars Hill Rd | 7340 | 2006-03-22 |  |  |  | 2006-04-07 | 2006-04-11
Fern Hill (C & G Only)
2400 Malcom Bridge Road | 7343 | 2006-03-22 |  |  |  | 2006-04-07 | 2006-04-11
Autumn Glen |  |  |  |  | 2006-04-14
2660 Rocky Branch Road | 7447 | 2006-03-28 |  |  | 2006-04-07 | 2006-04-28 | 2006-07-06
Clubside Plantation |  |  |  | 2006-05-16
1800 Barber Creek Road | 7001 | 2006-03-02 |  | 2006-03-31 | 2006-04-14 | 2006-05-19 | 2006-05-31
Boulder Springs Phase 4
New High Shoals Road | 7486 | 2006-03-29 |  |  | 2006-04-07 | 2006-04-14
Vintage Farms | resubmitted | 2006-04-12 | [5 empty] | C & G Only
Hodges Mill Road | 7630 | 2006-04-04 |  |  |  | 2006-04-21 | 2006-05-18 | 2006-04-20
Langford Business Park | [7 empty] | C & G
1400, 1420 Virgil Langford Road |  | 2006-02-08 |  |  |  | 2006-02-24 | 2006-07-31 | 2006-05-31
North Haven Phase I-IV |  |  |  | 5/19/06 rev
Choyce Johnson Road | 7778 | 2006-04-17 |  | 2006-04-18 | 2006-04-21 | 2006-05-19
Robinson Ridge |  |  |  | Never sent |  |  |  | See #15257
Whippoorwill Road | 7816 | 2006-04-18 |  | to Winder |  |  |  | 2008-04-18
Parkside Phase I (5 lots)
Hog Mountain/Mars Hill Rd | 7803 | 2006-04-18
Lea Haven
1302 & 1340 Daniells Bridge Road | 8082 | 2006-05-16 |  | 2006-05-18 | 2006-05-19 | 2006-06-16 | 2006-07-10
Fern Hill
2400 Malcom Bridge Road | 8083 | 2006-05-16 |  | 2006-05-18 | 2006-05-19 | 2006-06-16 | 2006-06-26
Hwy 15 S Water Line Ext.
Hwy 15 S | 8122 | 2006-05-18 |  | 2006-05-24 | 2006-05-26 | 2006-06-16 | 2006-06-20
Lakeview @ Jennings Mill | [6 empty] | C & G Only
1540 Meriweather Drive | 8157 | 2006-05-23 |  | 2006-05-31 | 2006-06-09 | 2006-06-23 | 2006-08-03
Lane Creek Plantation Phase 4 | resubmitted | 2006-07-17 |  |  | 2006-07-28 |  |  | C & G Only
Lane Creek Drive | 8212 | 2006-05-30 |  | 2006-05-31 | 2006-06-02 | 2006-08-04 | 2006-10-20 | 2006-08-17

## S.E. Log Pg 13
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
The Legends @ Oconee River
1082 Rossiter Court | 8214 | 2006-05-30 |  | 2006-05-31 | 2006-06-02 | 2006-06-16 | 2006-09-25
Boulder Springs Phase IV
New High Shoals Road | 8308 | 2006-06-09 |  |  |  | 2006-06-16 | 2006-06-19
Mars Hill Grading Plan
Mars Hill Road & Cliff Dawson Rd | 8359 | 2006-06-15 |  |  | 2006-06-23 | 2006-06-28 | 2006-07-11
Fairfield Meadows | [8 empty] | 5/06 to 8/06
Osborne Road | 8392 | 2006-06-20 |  |  | 2006-06-23 | 2006-07-31 | 2006-08-15
Daniells Bridge Road Grading Plan
Daniells Bridge Road | 8438 | 2006-06-27 |  | 2006-09-07 | 2006-09-15 | 2006-09-22 | 2006-09-27
Harperfield
Lenru Rd & Malcom Bridge Rd | 8497 | 2006-07-06 |  | 2006-07-11 | 2006-07-14 | 2006-07-28 | 2006-09-12
Oconee Plantation Center
1973 & 1975 Hog Mountain Road | 8670 | 2006-07-25 |  | 2006-07-26 | 2006-08-04 | 2006-09-15 | 2006-09-21
Pebble Creek Phase 2
Hwy 15/Greensboro Hwy | 8711 | 2006-07-31 |  | 2006-07-31 | 2006-08-04 | 2006-08-11 | 2006-08-15
Rowan Oak Estates (Phase 2)
2770 Rocky Branch Road | 8722 | 2006-08-01 |  | 2006-08-01 | 2006-08-04 | 2006-08-18 | 2006-09-21
Avalon
Lenru Road | 8730 | 2006-08-02 |  | 2006-08-03 |  | 2006-08-17 | 2006-10-11
Oconee Preschool Academy II
1420 Greensboro Hwy | 8784 | 2006-08-08 |  |  |  | 2006-08-11 | 2006-08-15
Princeton Farms Phase I & II | [6 empty] | Phase 1
Hwy 53 | 8908 | 2006-08-22 |  |  |  | 2006-09-08 | 2006-11-20
Club Estates | resubmitted | 2006-09-14
1280 Barber Creek Road | 8963 | 2006-08-29 |  | 2006-10-03 | 2006-10-06 | 2006-10-20 | 2006-12-08
Parkside Offsite SS, Reuse & LS
Hog Mtn, Mars Hill, Hodges Mill | 8980 | 2006-08-30 |  |  |  | 2006-09-15 | 2006-09-27
Witts Farm
2241 Old Bishop Road | 9215 | 2006-09-26 |  | 2006-09-26 | 2006-09-29 | 2006-10-13 | 2006-11-27
The Bend On The Apalachee | [7 empty] | C & G Only
2081 Macon Hwy | 9253 | 2006-09-29 |  | 2006-10-25 | 2006-11-03 | 2006-12-22 | 2007-05-04 | 2007-01-05
CVS/Pharmacy #4719 |  |  |  | 2006-10-31
2080 Hog Mountain Road | 9303 | 2006-10-06 |  | 2006-10-11 | 2006-10-13 | 2006-11-03 | 2007-01-25
The Landing @ Parkside
3100 Hog Mtn Road | 9377 | 2006-10-16 |  | 2006-10-16 |  | 2006-10-20 | 2007-01-30
Epps Bridge Corner
1761 Epps Bridge Pkwy | 9402 | 2006-10-17 |  |  |  | 2006-10-20 | 2007-01-17
Bishop Pointe Preserve |  | 2006-10-24
Price Mill Road | 9404 | 2006-10-17 |  | 2006-10-25 | 2006-11-03 | 2006-12-15 | 2007-01-18

## S.E. Log Pg 14
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Parkside Phase 2 |  |  |  |  | 2006-12-15
Hwy 53 & Mars Hill Road | 9408 | 2006-10-17 |  | 2006-10-25 | 2006-11-03 | 2007-01-05
Price Estate | [7 empty] | Not Needed
2323 Hodges Mill Road | 9450 | 2006-10-23 |  | 2006-10-25 | 2006-11-03
Wilkes Meadows
1221 Greene Ferry Road | 9454 | 2006-10-24 |  | 2006-10-25 | 2006-11-03 | 2006-11-08 | 2007-01-02
Wildflower Meadows Phse I | [8 empty] | 10/06 to 6/07
Dials Mill Road | 9516 | 2006-10-31 |  | 2006-11-02 |  | 2006-11-03 | 2007-03-23
Habersham | [7 empty] | Plans in
2960 Rocky Branch Road | 9554 | 2006-11-07 |  | 2006-11-07 |  | 2006-11-08 |  | Attic
Oconee Decorative Arts Center
3161 Hog Mountain Road | 9564 | 2006-11-07 |  | 2006-11-07 | 2006-11-08 | 2007-01-02 | 2007-03-07
Oconee County Middle School |  |  |  |  | 2007-02-09
1101 Mars Hill Road | 9839 | 2006-12-15 |  | 2007-01-24 | 2007-01-25 | 2007-03-02 | 2007-03-07
The Georgia Club | [6 empty] | C & G Only 2/27/07
Barber Creek Drive | 10153 | 2007-01-16 |  | 2007-01-24 |  | 2/9/007 | 2007-04-27
IHOP |  |  |  | 2007-02-06 | 2007-02-09
1061 Parkway Place | 10359 | 2007-01-23 |  | 2007-01-24 | 2007-01-25 | 2007-02-16 | 2007-04-09
Oldfield |  |  |  |  | 2007-03-02
Clotfelter Road | 10487 | 2007-01-30 |  | 2007-01-31 | 2007-02-02 | 2007-03-09 | 2007-03-26
Meadow Springs Amenity Area
1050 Broomsedge Drive | 10557 | 2007-02-02 |  | 2007-02-07 | 2007-02-09 | 2007-03-02 | 2007-03-07
Rocky Branch Elem
5250 Hog Mountain Road | 10672 | 2007-02-09 |  |  |  | 2007-03-09 | 2007-03-15
Langford Estates |  |  |  |  | 2007-03-23
1141 S Poss Lake Dr/1111 Lake Pointe Dr | 10796 | 2007-02-20 |  | 2007-02-27 | 2007-03-02 | 2007-04-06 | 2007-05-21
Wildflower Meadows Phse 2
Dials Mill | 10903 | 2007-02-27 |  |  |  | 2007-03-22 | 2007-04-16
Bishop Farms Pkwy South Rd Ext |  |  |  |  | 2007-05-25
Bishop Farms Pkwy South | 11357 | 2007-03-27 |  | 2007-03-28 | 2007-03-30 | 2007-06-01 | 2007-06-27
Glacier Park
Moores Ford Road | 11551 | 2007-04-02 |  |  | 2007-04-13 | 2007-05-25 | 2007-07-17
Bear Creek 24 Inch Connector
| 11854 | 2007-04-27 |  |  | 2007-05-04 | 2007-06-08 | 2007-06-14
Stonewood |  |  |  |  | 2007-05-18
1550 Union Chruch Road | 11879 | 2007-04-30 |  |  | 2007-05-04 | 2007-06-22 | 2007-08-14
Oconee Safe Storage
1711 Hog Mtn Road | 12176 | 2007-06-05 |  |  | 2007-06-08 | 2007-07-27 | 2007-07-30
OB Watkinsville (Center 53)
2201/2203 Hog Mtn Rd | 12193 | 2007-06-06 |  |  | 2007-06-29 | 2007-08-10 | 2007-09-11

## S.E. Log Pg. 15
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments | Disturbed Acres
Cottages of Watkinsville
Simonton Bridge Road | 12288 | 2007-06-20 |  |  | 2007-07-19 | 2007-07-27 | 2007-07-30
South Watkinsville Sanitary Sewer
Watkinsville | 12345 | 2007-06-28 |  |  |  | 2007-07-11 | 2007-07-12
NW Woods Water Dist. System
Northwest Woods Subdivision | 12429 | 2007-07-09 |  |  |  | 2007-07-13 | 2007-07-19
Hwy 441 North Sanitary Sewer
Hwy 441 (Hog Mtn to Rockinwood) | 12576 | 2007-07-31 |  |  | 2007-08-03 | 2007-09-19 | 2007-09-26
Grace Baptist Church
6401 Hog Mountain Road | 12775 | 2007-08-28 |  |  | 2007-10-03 | 2007-10-18 | 2007-12-03
Malcom Bridge Middle Add./Renovation
2500 Malcom Bridge Road | 12661 | 2007-08-10 |  | 2007-08-15 | 2007-08-22 | 2007-08-28 | 2007-09-10
Bethabara Baptist Church
4651 Monroe Hwy (C & G Only) | 12872 | 2007-09-11 |  |  | 2007-09-18 | 2007-10-03 | 2007-10-11
New Life Apostolic Church
Bishop Farms Parkway South | 12633 | 2007-08-07 |  |  | 2007-08-22 | 2007-09-19
Glacier Park Phase II
Moores Ford Road | 13138 | 2007-11-05 |  |  | 2007-11-21 | 2007-12-21 | 2008-03-03
2271 Hog Mountain Road C & G Only
Hog Mountain Road | 13143 | 2007-11-05
Founder's Grove Phase IV |  |  |  |  | 1/2 & 1/9/08
Hearthstone Way | 13187 | 2007-11-13 |  |  | 2007-11-21 | 2008-01-30 | 2008-05-29
The Heights of Oconee
Macon Hwy | 13246 | 2007-11-29 |  |  |  | 2008-01-02 | 2008-03-31
Hotel at Virgil Langford Business Park
Langford Drive | 13339 | 2007-12-17 |  |  | 2008-01-02 | 2008-01-30 | 2008-03-25
First Ga Bank
Virgil Langford & Jennings Mill Rd | 13338 | 2007-12-17 |  |  | 2008-01-02 | 2008-01-30 | 2008-03-28
Spring Hill Suites Mariott | [7 empty] | per BR, Steve
3500 Daniells Bridge Road | 13355 | 2007-12-19 |  |  |  | 2008-02-06 | 2008-03-18 | & Emil
Medical Offices @ 1500 Langford Dr
1500 Langford Drive | 13816 | 2008-01-22 |  |  | 2008-01-30 | 2008-02-06 | 2008-03-04 |  | 1.87
Lot 1 Parkway Shops @ Epps Bridge
1021 Parkway Place | 13892 | 2008-01-28 |  |  |  | 2008-01-30 | 2008-02-01 |  | 2.2
The Georgia Club Neighborhood D | [6 empty] | C&G 4/25/08
1050 Chancellors Dr | 14429 | 2008-03-04 |  |  |  | 2008-04-23 | 2008-06-25
Robinson Ridge
2070 Whippoorwill Road | 15257 | 2008-04-18 |  |  | 2008-04-30 | 2008-05-16
Athens Academy Preschool Center
1281 Spartan Lane | 15360 | 2008-04-30 |  | 2008-05-07 |  | 2008-05-21 | 2008-05-30

## S.E. Log Pg. 16
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Beaumont
Hwy 53 | 15439 | 2008-05-12 |  |  |  | 2008-06-03 | 2008-06-18
Prince Avenue Baptist Church
2131 Ruth Jackson Road | 15765 | 2008-06-13 |  |  |  | 2008-06-25 | 2008-06-25
Elder Ridge & Laurel Chase Wtr Sys
Elder Road | 16131 | 2008-08-15 |  |  |  | 2008-10-22 | 2008-10-27
Legacy Business Park | [6 empty] | C & G 10/2/08
1800 Hog Mtn Rd | 16164 | 2008-08-21 |  |  | 2008-09-17 | 2008-09-24 | 2009-01-07
Oconee High School Gym
2721 Hog Mountain Road | 16245 | 2008-09-09 |  |  |  | 2008-09-17 | 2008-09-23
Athens Georgia Stake Center | [6 empty] | C & G 1/5/09
1080 Julian Drive | 16287 | 2008-09-16 |  |  |  | 2008-10-08 | 2009-04-01
Georgia Bank & Trust
2431 Hog Mountain Road | 16571 | 2008-12-02 |  |  | 2008-12-17 | 2009-01-28 | 2009-03-19
St. Marys Alzheimers Clinic
1660 Jennings Mill Road | 17337 | 2009-02-19 |  |  |  | 2009-07-22 | 2009-07-24
Watkinsville 1st UMC
1331 New High Shoals Road | 18264 | 2009-05-05 |  |  |  | 2009-06-29 | 2009-07-01
Lampkin Branch Sanitary Swr Replacement
Lampkin Branch Sewer | 18499 | 2009-05-21 |  |  |  | 2009-06-03 | 2009-06-16
Watkinsville First Baptist Church
1610 Simonton Bridge Road | 18559 | 2009-06-02 |  |  |  | 2009-06-29 | 2009-07-01
Highland Park (Beaumont)
Hwy 53 | 18757 | 2009-07-01
Westminster Christian Academy
1640 New High Shoals Road | 18781 | 2009-07-09 |  |  |  | 2009-08-05 | 2009-08-06
Apalachee Mitigation |  | 2010-02-19
Off Lake Oconee Road | 18814 | 2009-07-16 |  |  |  | 2010-03-19 | 2010-03-23
Quiktrip
1240 Oconee Connector | 18888 | 2009-08-05 |  |  |  | 2009-09-09 | 2009-11-02
Houseman Pest
Ga Hwy 24 - 441 | 19151 | 2009-10-16 |  |  |  | 2009-10-21 | 2009-11-16
Calls Creek Pump Station & Headworks
NOT NEEDED | 19736 | 2010-01-21
Jennings Mill Pkwy Borrow Pit |  |  |  |  | 2010-03-26 | 2010-06-30 | 2010-07-01 | 10.91 acres
Jennings Mill Road | 20156 | 2010-03-10 |  |  | 2010-03-17 | 2010-04-07 | 2010-04-09
Hog Mountain Road C & G |  |  |  |  | 2010-04-02
2271 Hog Mountain Road |  | 2010-03-22 |  |  |  | 2010-06-04 | 2010-06-11 | 4.46 acres
North Oconee Sewer Ext. |  |  |  |  | 2010-04-14
Along McNutt Creek | 20414 | 2010-03-26 |  |  |  | 2010-05-03 | 2010-05-10 | 3.06 acres

## S.E. Log Pg 17
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Rocky Branch LAS Site
(Site 2) | 20997 | 2010-06-02 |  |  |  | 2010-06-30 | 2010-07-01 | 5.58 acres
Veterans Park
(Site 3) | 20996 | 2010-06-02 |  |  |  | 2010-06-30 | 2010-07-01 | 2.96 acres
Athens Academy South Access Drive
2081 Spartan Lane | 21072 | 2010-06-24 |  |  | 2010-07-09
Jennings Mill Borrow Site #2
Jennings Mill Road | 21445 | 2010-10-25 |  |  |  | 2010-11-05 | 2010-11-05 | 2.9 acres
Oconee Waste Transport
1750 Greensboro Hwy | 21591 | 2010-12-10 |  |  | 2010-12-31 | 2011-02-07 | 2011-02-07 | 6 acres
Meridian Phse II
3751 Mars Hill Road | 22552 | 2011-03-24 |  |  |  | 2011-05-03 | 2011-05-25 | 1.6 acres
Virgil Langford Business Park
1220 Langford Drive | 22799 | 2011-04-07 |  |  | 2011-05-19 | 2011-05-25 | 2011-05-25 | 1.62 acres
Goat Farm Road Mitigation Bank |  |  |  | Resubmittal | 2011-07-11
1461 Goat Farm Road | 23149 | 2011-05-26 |  | 2011-10-17 | 2011-11-09 | 2011-12-14 | 2011-12-16 | 8.65 acres
Heritage Park Mitigation
(Site 1) |  | 2011-05-27 |  |  | 2011-06-22 | 2011-07-11 | 2011-07-13 | 8.11 acres
Oconee Gymnastics
1090 Jamestown Blvd (lot 4B) | 23284 | 2011-06-24 |  |  | 2011-07-29 | 2011-07-24 | 2011-07-24 | 1.50 acres
Langford Business Park Lots 2 & 3
1181 & 1471 Langford Drive | 23291 | 2011-06-24 |  |  |  | 2011-07-29 | 2011-08-03 | 4 acres
Epps Bridge Center |  |  |  |  | 2011-11-02
Oconee Connector Ext. | 23671 | 2011-09-29 |  |  | 2012-01-06 | 2012-02-03 | 2012-03-09 | 64.8 acres
Dr. Harter
1020 Jamestown Blvd | 25533 | 2011-09-29 |  |  | 2011-10-28 | 2011-12-02 | 2012-02-15 | 1.5 acres
RaceTrac
Mars Hill & 78 | 23704 | 2011-10-10 |  |  | 2011-11-02 | 2011-12-02 | 2011-12-16 | 4.2 acres
Camp General Store
US Hwy 78 & 53 | 23784 | 2011-10-31 |  |  | 2011-11-21 | 2012-01-13 | 2012-01-18 | 6.55 acres
Highland Park
Hog Mountain/Hwy 53 |  | 2012-03-30 |  |  | 2012-04-20 | 2012-05-09 | 2012-05-10 | 12.67 acres
National Tire & Battery |  |  |  |  | 2012-08-06
Jordan Drive | 25069 | 2012-03-30 |  | 2012-04-11 | 2012-04-30 | 2012-10-22 | 2012-10-23 | 1.13 acres
Lowe's Out Parcels
1851 Epps Bridge Pkwy |  |  |  |  | 2012-06-01 | 2012-06-29 |  | 3.0 acres
Elite Gymnastics
1010 Lampkin Branch Drive | 25366 | 2012-04-30 |  | 2012-05-02 | 2012-05-18 | 2012-06-29 | 2012-07-09 | 2.40 acres
Athens Academy Middle School Activity Cntr
1281 Spartan Lane | 25461 | 2012-05-11 |  |  | 2012-06-29 | 2012-07-20 | 2013-09-06 | 2.15 acres

## S.E. Log Pg. 18
| NUMBER | DATE REC'D | RET'D TO DEV | SENT TO WINDER | UNAPPROVED | APPROVED | RELEASED | Comments
Farmington Fire Station
2590 Old Farmington Rd | 25510 | 2012-05-23 |  |  | 2012-06-15 |  | 2012-08-13 | 4.30 acres
Golden Chick
7990 Macon Hwy | 25786 | 2012-07-19 | [5 empty] | .964 acres
316 Professional Quarter Lot 3
1747 Langford Drive | 25787 | 2012-07-19 |  |  | 2012-08-08 | 2012-08-13 |  | 2.16 acres
Epps Bridge Centre - Outparcel 10
1791 Oconee Connector | 27021 | 2013-01-23 |  |  |  | 2013-03-06 | 2013-04-18 | .85 acres
Georgia Skin Cancer & Aesthetic Derm
1171 Epps Bridge Pkwy | 27365 | 2013-02-25 |  |  | 2013-03-27 |  | 2013-05-31 | 2.53 acres
LCN Oconee (road)Resurgence Park | [7 empty] | 10.36 acres
1171 Epps Bridge Pkwy | 27366 | 2013-02-25 |  |  | 2013-03-27 | 2013-05-01 | 2013-05-31 | 6.1 acres
Meadow Springs Phase 3
Orchard Dr, Dragonfly Way, Meadow Lake | 27400 | 2013-03-01 |  |  |  | 2013-05-16 | 2013-06-10 | 13.86 acres
Daniels Bridge Promenade |  |  |  |  | 2013-07-08
Daniels Bridge & Mars Hill | 28012 | 2013-04-03 |  | 2013-04-05 | 2013-05-08 | 2013-09-04 | 2013-09-04 | 5.92 acres
Meadow Springs Amenity Area
1050 Orchard Drive | 28070 | 2013-04-09 |  |  |  | 2013-05-08 | 2013-06-11 | 1.9 acres
Oconee Gymnastics Center Phase II
1090 Jamestown Blvd | 28246 | 2013-04-25 |  |  | 2013-05-16 | 2013-06-28 | 2013-07-05 | 1.187 acres
316 Professional Qtr Phase 4 | [6 empty] | C&G 6/18/13
1360 & 1390 Virgil Langford Rd | 27317 | 2013-02-19 |  |  | 2013-03-06 | 2013-05-01 | 2013-06-21 | 10.97 acres
Athens Ridge Townhomes
8830 Macon Hwy | 28825 | 2013-06-25 |  |  |  | 2013-07-17 | 2013-08-02 | 24.38 acres
Plant Sciences Farm Remediation
1280 Snows Mill Rd | 29707 | 2013-09-26 |  |  | 2013-10-28
Athens Academy Soccer Field
1281 Spartan Lane | 29986 | 2013-10-21 |  |  | 2013-11-12 | 2014-01-10 | 2014-02-27 | 2.1 acres
Thrive Senior Living Center
Resurgence Park | 30941 | 2013-12-30 |  |  | 2014-01-27 | 2014-03-05 | 2014-04-10 | 4.56 acres
Whippoorwill Rd Wtr Main Ext
Whippoorwill Road | 30626 | 2013-12-05 |  |  | 2014-01-06 | 2014-02-20 | 2014-02-21 | 3.57 acres
Epps Bridge Centre - Outparcels 2 & 4
1791 Oconee Connector | 31413 | 2014-01-31 |  |  | 2014-03-21
Connecting Point Church
Lenru Road | 31672 | 2014-02-21 |  |  |  | 2014-03-21 | 2014-05-07 | 4.7 acres
Kroger Fuel Center (GA-435)
Oconee Connector | 31693 | 2014-02-24 |  |  | 2014-03-21 | 2014-04-15 | 2014-04-17 | 1.19 acres
The Falls of Oconee | [6 empty] | C & G 9/27/14
8831/8851/8861 Old Macon Hwy | 32283 | 2014-03-31 |  |  | 2014-04-15 |  | 2014-10-14 | 3.42 acres
Sentry Self Storage
Virgil Langford Road | 33363 | 2014-07-03 |  |  |  | 2014-08-29 | 2014-08-29 | 4.0 acres

## S.E. Log Pg. 19
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Washington | UNAPPROVED | APPROVED | RELEASED | Comments
McNutt Creek Sewer Connector
Jimmy Daniel to Epps Bridge | 33369 | 2014-07-07 |  | 2014-07-14 |  | 2014-08-29 | 2014-08-29
Downs Creek Farm
1531 Daniells Bridge Road | 33408 | 2014-07-09 |  | 2014-07-14 |  | 2014-08-29 | 2014-09-22 | 11.9 acres
Connecting Point
Lenru Road | 33803 | 2014-08-26 |  | 2014-08-27 | 2014-09-11 |  | 2014-10-08 | 7.15 acres
2271 Hog Mountain Road
2271 Hog Mountain Road | 33958 | 2014-09-15 |  | 2014-09-17 |  |  | 2014-10-09 | 4.46 acres
Caterpillar Parking Lot Expansion
Dozier Drive | 34082 | 2014-09-25 |  | 2014-09-26 |  | 2014-10-22 | 2014-10-31 | 6.47 acres
Gunter Property Phase I-Lavista Office
8120 & 8130 Macon Hwy | 34276 | 2014-10-21 |  |  |  | 2015-01-26 | 2015-01-29 | 11.78 acres
Pebble Creek Phase 1
Lots 3-31 & 35 | 34499 | 2014-11-19 |  | 2014-11-20
The Summit Phase 2A & 2B | [6 empty] | C&G 4/2/15
3651 Mars Hill Road | 35235 | 2015-01-22 |  |  |  | 2015-01-29 | 2015-05-06 | 5.81 acres
Malcom Bridge Middle School
2500 Malcom Bridge Road | 35249 | 2015-01-23 |  |  |  | 2015-02-10 | 2015-02-10 | 2.52 acres
Bone Island Grillhouse
2055 Oconee Connector | 36088 | 2015-03-20 |  | 2015-03-23 | 2015-03-30 | 2015-04-29 | 2015-05-06 | 1.6 acres
Mars Hill Business Park | [7 empty] | Released for grading only 5/4/15
1131,1140,1141 Commerce Drive | 36648 | 2015-04-15 |  | 2015-04-15 |  | 2015-05-04 | 2015-06-18
316 Professional Qtr Phase V | [6 empty] | 6/3/2015 C&G
Jennings Mill & Virgil Langford | 37625 | 2015-05-12 |  |  |  | 2015-06-02 | 2015-08-12 | 15.42 acres
Fairways CCRC Phase I |  |  |  | took to UPS | 2015-08-18
1900 Langford Drive | 37499 | 2015-06-02 |  | 2015-06-03 |  | 2015-11-20 | 2015-12-31 | 13.3 acres
NW Quadrant Borrow Pit |  |  |  | 2015-09-16
Mars Hill & Cliff Dawson Rd | 38387 | 2015-09-15 |  | Rcd 9/17/15 | 2015-09-22 | 2015-10-15 | 2015-10-20 | 4.4 acres
Epps Bridge Road Force Main Upgrade
| 38835 | 2015-11-05 |  | 2015-11-06 |  | 2015-12-10 | 2015-12-14 | 7.7 acres
Lane Creek Plantation
Lots 14-19,96-99,102-105,106-109 | 39030 | 2015-12-08 |  |  | 2016-01-04 | 2016-01-20 | 2016-01-21 | 9.451 acres
Four Seasons Carwash
1035 Parkway Place | 39701 | 2016-01-25 |  | 2016-01-26 | 2016-02-17 | 2016-03-07 | 2016-03-14 | 1.34 acres
Mars Hill Business Park Lot 16
1041 Commerce Court | 40036 | 2016-02-15 |  | 2016-02-16 |  | 2016-03-29 | 2016-04-06 | 1.14 acres
Vac B-2 Retail Center |  |  |  | TOOK TO UPS STORE
8830 Old Macon Hwy | 40323 | 2016-03-02 |  | 2016-03-03 |  | 2016-04-13 | 2016-06-14 | 6.336 acres
441 South Business Park |  |  |  |  | 2016-07-19
New High Shoals Road | 41034 | 2016-04-01 |  | 2016-04-01 | 2016-04-20 | 2016-09-13 | 2016-09-13 | 8.90 acres
Lane Creek Plantation
Lots 22-29, 77 &111-114 | 41303 | 2016-04-19 |  |  |  | 2016-05-11 | 2016-05-18 | 4.315 acres

## S.E. Log Pg. 20
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Washington | UNAPPROVED | APPROVED | RELEASED | Comments
Lane Creek Plantation | [5 empty] | 2016-05-17 |  | 2.361 acres
Lots 30-37, 58, 66, 66A & 66B | 41499 | 2016-05-02 |  | 2016-05-03 |  | 2016-05-18 | 2016-05-20 | 4.932 acres
Athens Academy Admin. Bldg | [6 empty] | 2016-09-06
1281 Spartan Lane | 41758 | 2016-05-26 |  | 2016-05-27 |  | 2016-06-30 | 7/1/2016 Grading | .87 acres
Watkinsville 1st Baptist Church Parking
1610 Simonton Bridge Road | 42000 | 2016-06-10 |  | 2016-06-10 |  | 2016-07-13 | 2016-08-15 | 4 acres
National EMS
1021 Lampkin Branch Dr | 42116 | 2016-06-20 |  |  | 2016-07-15 | 2016-08-16 | 2016-08-17 | 2.29 acres
Epps Bridge Centre II & III | [6 empty] | 9/15/16 Grading
1270 Jennings Mill Rd | 42201 | 2016-06-28 |  |  | 2016-07-18 | 2016-08-18 | 2016-09-30 | 70.2 acres
Utility Department
Rays Church Road Water Main Ext. | 42951 | 2016-09-08 |  |  | 2016-09-29 | 2016-11-22 | 2016-12-02 | .90 acres
Stonebride Partners Hwy 53 Development | [6 empty] | 2016-10-10
2271 Hog Mountain Road | 43113 | 2016-09-23 |  |  |  | 2016-10-07 | C & G Only | 5.6 acres
Dollar General Bogart
1031 Garland Drive | 43442 | 2016-09-25 |  | 2016-09-26 |  | 2016-11-16 | 2016-11-17 | 1.86 acres
Old Bishop Road Water Main Extension
Old Bishop Road | 43502 | 2016-11-01 |  | 2016-11-02 |  | 2016-11-22 | 2016-12-02 | 2.9 acres
Connector 1357 | [8 empty] | Common Development
1357 Oconee Connector | 43650 | 2016-11-21 |  | 2016-11-22 | 2016-12-16 | 2017-03-10 | 2017-03-22 | 7.5 acres | Primary
Athens Academy Middle School Activity Cntr | [8 empty] | Stand Alone
1281 Spartan Lane | 43679 | 2016-11-22 |  | 2016-11-23 | 2016-12-07 | 2017-02-23 | 2017-03-29 | 2.3 acres | Primary
Resurgence Park Lots 2, 8 & 9 | [6 empty] | 2017-01-05 |  | Stand Alone
1400,1355,2055 Resurgence Drive | 43851 | 2016-12-07 |  | 2016-12-08 |  | 2017-01-04 | C & G Only | 6.65 acres | Primary
Oconee Elementary School #7 | [8 empty] | Stand Alone
7921 Hog Mountain Road | 44329 | 2017-01-12 |  | 2017-01-12 |  | 2017-02-16 | 2017-02-17 | 37.8 acres | Primary
Presbyterian Homes of Georgia | [8 empty] | Stand Alone
8161 Macon Hwy | 45004 | 2017-02-27 |  | 2007-03-17 |  | 2017-04-21 | 2017-09-21 | 65.46 acres | Primary
Georgia Club - Barber Creek South Sec. C1 & F1 |  |  |  | UPS |  |  |  |  | Common Development
Georgia Club Drive | 45202 | 2017-03-08 |  | 2017-03-08 |  | 2017-04-13 | 2017-04-14 | 17.1 acres | Primary
Rhino Storage | [8 empty] | Stand Alone
Macon Hwy | 45679 | 2017-03-29 |  | 2017-03-30 | 2017-05-03 | 2017-06-06 |  | 4.1 acres | Primary
Texas Roadhouse | [8 empty] | Stand Alone
1021 Dowdy Road | 45683 | 2017-03-29 |  | 2017-03-29 |  | 2017-05-02 | 2017-07-11 | 2.0 acres | Primary
Spartan Estates | [8 empty] | Common Development
Spartan Lane | 45839 | 2017-04-03 |  |  | 2017-05-03 | 2017-05-19 | 2017-05-30 | 11.9 acres | Primary
Athens Academy Parking Lot Addition | [8 empty] | Stand Alone
1281 Spartan Lane | 46337 | 2016-04-27 |  |  |  | 2017-05-16 | 2017-05-26 | 1.84 acres | Primary
OVP Pump Station & Force Main | [8 empty] | Infastructure
3500 Hog Mountain Road | 46459 | 2017-05-08 |  | 2017-05-08 | 2017-05-31 | 2017-06-26 |  | 2.2 acres | Primary
University of North Georgia | [8 empty] | Stand Alone
1201 Bishop Farms Pkwy | 46589 | 2017-05-16 |  |  | 2017-06-26 | 2017-07-25 | 2017-07-25 | 1.23 acres | Primary

## S.E. Log Pg. 21
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Washington | UNAPPROVED | APPROVED | RELEASED | Comments
Oconee Elem. School # 7 (Revised) |  |  |  | Hand Del. To R.Amos |  |  |  |  | Stand Alone
7921 Hog Mountain Rd | 44329 | 2017-05-17 |  | 2017-05-19 |  | 2017-06-14 | 2017-06-26 | 32.6 acres | Primary
Resurgence Park Lot 5 (C & G Only) | [8 empty] | Stand Alone
1780 Resurgence Drive | 46737 | 2017-05-26 | [5 empty] | 3.6 acres | Primary
Jimmy Daniell Professional Offices | [8 empty] | Stand Alone
1381 Jimmy Daniell Rd | 46756 | 2017-05-31 |  |  |  | 2017-07-28 | 2017-07-31 | 1.6 acres | Primary
Athens Oconee Dentistry | [8 empty] | Stand Alone
Virgil Langford Rd | 46881 | 2017-06-08 |  |  | 2017-07-20 | 2007-08-01 | 2007-08-03 | 1.2 acres | Primary
Mercedes-Benz of Athens | [6 empty] | 9/15/17 C & G |  | Stand Alone
1590 Virgil Langford Rd | 46973 | 2017-06-19 |  |  | 2017-07-20 | 2017-09-14 | 2017-10-03 | 19.1 acres | Primary
Pinelake Campground |  |  |  |  | 2017-09-14 |  |  |  | Stand Alone
5630 High Shoals Road | 47194 | 2017-07-10 |  | 2017-07-11 | 2017-08-03 | 2018-01-30 |  | 9.4 acres | Primary
Briarwood Baptist Church Addition |  |  |  |  | 2017-08-04 |  |  |  | Stand Alone
1900 Robinhood Road | 47224 | 2017-07-12 |  |  | 2017-08-15 | 2017-08-17 | 2017-09-19 | 11.4 acres | Primary
Oconee Veterans Park Expansion | [8 empty] | Stand Alone
3500 Hog Mountain Road | 47474 | 2017-08-04 |  | 2017-08-07 | 2017-08-28 | 2017-09-06 | 2017-09-07 | 16.92 acres | Primary
OCHS Additions | [8 empty] | Stand Alone
2721 Hog Mountain Road | 47709 | 2017-08-24 |  |  | 2017-09-18 | 2017-09-27 | 2017-09-28 | 1.27 acres | Primary
OCUD | [8 empty] | Infastructure
2018 Water System Improvement | 47712 | 2017-08-24 |  |  | 2017-09-27 | 2017-10-05 |  | 5.0 acres | Primary
Malcom Bridge Estates | [8 empty] | Common Dev.
2241-2201 Malcom Bridge Road | 47816 | 2017-09-06 |  |  | 2017-09-20 |  |  | 32.5 acres | Primary
The Grove nka Summerfield |  |  |  |  | 2017-12-11 |  | C&G 1/12/18 |  | Common Dev.
6651 Hog Mountain Road | 47957 | 2017-09-27 |  | 2017-09-28 | 2017-10-04 | 2018-01-02 | 2018-02-12 | 2.8 acres | Primary
Boswell Electric |  |  |  |  | 2017-12-12 |  | 12/15/17 C&G |  | Stand Alone
Ga Hwy 316 | 48366 | 2017-11-22 |  |  | 2017-11-30 | 2017-12-14 | 2018-03-05 | 11.1 acres | Primary
1st Madison Bank & Trust | [8 empty] | Stand Alone
Mars Hill & Daniells Bridge Rd | 48520 | 2017-12-06 |  |  | 2017-12-14 | 2018-01-22 | 2018-03-20 | 1.8 acres | Primary
Princeton Farms - Amenity Lot |  |  |  |  | 1/31-4/30-5/10-6/7 |  |  |  | Common Dev.
1341 Princeton Farms Drive | 48943 | 2018-01-12 |  |  | 2018-06-19 | 2018-06-19 | 2018-09-10 | 8.5 acres | Primary
OCHS Track Renovations |  |  |  |  | 2018-02-28 |  |  |  | Stand Alone
2721 Hog Mountain Road | 49327 | 2018-02-12 |  | 2018-02-13 | 2018-02-16 | 2018-03-08 | 2018-03-12 | 2.3 acres | Primary
NOHS Track Renovations |  |  |  |  | 2018-02-28 |  |  |  | Stand Alone
1081 Rocky Branch Road | 49328 | 2018-02-12 |  | 2018-02-03 | 2018-02-15 | 2018-03-08 | 2018-03-12 | 2.5 acres | Primary
Robins Federal Credit Union | [8 empty] | Common Dev.
2273 Hog Mountain Road | 49717 | 2018-03-08 |  |  | 2018-03-22 | 2018-04-02 | 2018-04-04 | .91 acres | Tertiary
Fire Station # 8 |  |  |  |  | 2018-03-27 |  |  |  | Stand Alone
1600 Virgil Langford Road |  | 2018-03-06 |  |  | 2018-03-12 | 2018-04-02 | 2018-04-02 | 2.9 acres | Primary
Lakewood Amenity @ The Ga Club | [7 empty] | 3.26 acres Barrow Co | Common Dev.
Georgia Club Drive |  | 2018-04-20 | [5 empty] | 2.6 accres | Secondary
Stonewood |  |  |  |  | 2018-08-28 |  |  |  | Primary
Union Church Road | 50797 | 2018-05-03 |  |  | 2018-05-15 | 2018-08-30 | 2018-09-11 | 78.17 acres | Common Dev

## S.E. Log Pg. 22
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Winder | UNAPPROVED | APPROVED | RELEASED | Comments
The Standard, Senior Living | [8 empty] | Primary
2881 Monroe Highway | 51105 | 2018-05-29 |  | 2018-05-30 | 2018-06-06 | 2018-07-16 | 2018-07-17 | 1.6 acres | Stand Alone
CZ Holdings, LLC | [8 empty] | Primary
1051 Commerce Court | 51107 | 2018-05-29 |  | 2018-05-30 | 2018-06-18 | 2018-06-28 | 2018-08-15 | 1.2 acres | Stand Alone
Lake Welbrook Dam Renovation | [8 empty] | Primary
Lake Welbrook Drive | 51109 | 2018-05-29 |  | 2018-05-30 | 2018-06-18 | 2018-06-29 | 2018-07-02 | 2.8 acres | Stand Alone
Crimson Pointe | [8 empty] | Primary
1390 Malcom Bridge Road | 51713 | 2018-07-17 |  | 2018-07-17 | 2018-07-27 | 2018-08-22 | 2018-09-04 | 2.0 acres | Stand Alone
Briarwood Baptist Church Bldg Add Rev |  |  |  |  | 2018-09-17 |  |  |  | Primary
1900 Robinhood Road | 47224(Rev) | 2018-08-28 |  | 2018-08-29 | 2018-09-26 | 2018-10-11 | 2018-10-15 | 11.40 acres | Stand Alone
Highway 441 Car Wash | [8 empty] | Primary
1000 Hog Mountain Road | 52518 | 2018-10-01 |  | 2018-10-02 | 2018-10-25 | 2018-11-30 | 2018-12-27 | 1.788 acres | Stand Alone
Somerset Lots 2A & 2B
Heather Lane | 52641 | 2018-10-16 |  | 2019-10-19 |  | 2018-10-26 | 2018-10-30 | 1.55 acres
Watkinsville First Baptist Church |  |  |  |  | 2019-01-03
1610 Simonton Bridge Road | 52987 | 2018-11-20 |  | 2018-11-26 | 2018-12-11 | 2019-01-08 | 2019-01-16 | 2.0 acres
PABC Parking Lot Expansion |  | 1/4/19 resubm |  | 2019-01-07
2131 Ruth Jackson Road | 52989 | 2018-11-21 |  | 2018-11-26 | 2018-12-13 | 2019-01-10 | 2019-01-30 | 2.53 acres
Lakewood Village |  |  |  |  | 2018-10-30
Georgia Club Drive |  |  |  |  | 2018-11-27
Advanced Urology Headquarters |  |  |  | Took to UPS | 2019-01-08
1272 Virgil Langford Raod | 53172 | 2018-12-06 |  | 2018-12-07 | 2018-12-19 | 2019-01-10 |  | 1.5 acres
Burgess Residence |  |  |  | Took to UPS
Lots 11 & 12 Vintage Drive | 53208 | 2018-12-10 |  | 2018-12-10 |  |  |  | 1.56 acres
Butler's Crossing Professional Park |  |  |  |  | 2018-09-10
2053 Experiment Station Road | 52033 | 2018-08-16 |  |  | 2018-10-24 | 2018-12-10 | 2019-01-24 | 6.71 acres
Stonewood Phase 1
1530 Union Church Road | 52758 | 2018-10-31 |  | 2018-11-19 |  | 2018-12-12 | 2019-01-18 | 9.89 acres
John & Jennifer Hadden
1110 Cliff Dawson Road | 53281 | 2018-12-13 |  |  | 2018-12-20 | 2019-01-22 | 2019-01-23 | .50 acres
The Roscoe Residence
2790 Vintage Drive | 53508 | 2018-12-31 |  | 2019-01-02 |  | 2019-01-15 | 2019-01-22 | .94 acres
Bruster's | Tertiary
Parkway Blvd |  | 2019-01-08 |  | 2019-01-09 | 2019-01-14 | 2019-01-23 | 2019-01-28 | .711 acres
Tertiary
1271 W Fitzgerald Lane |  | 2019-01-17 |  | 2019-01-18 |  | 2019-01-24 | 2019-01-25 | .89 acres
Stephen & Donna Kinnaird | Tertiary
1727 Wild Azalea Lane |  | 2019-01-28 |  | 2019-01-29 | 2019-02-22 | 2019-03-13 | 2019-03-15 | 2.0 acres
Barber Creek Sewer Extension
| 54339 | 2019-02-26 |  | 2019-02-27 | 2019-04-18 |  |  | 7.4 acres
Residential Shared Access Drive
2070 Hodges Mill Road |  | 2019-03-22 |  | 2019-03-26 | 2019-05-01 | 2019-06-10 |  | 3.80 acres
Scott Beaver
2154 Edge Water Drive |  | 2019-03-28 |  | 2019-03-29 | 2019-05-02 |  |  | 1.2 acres

## S.E. Log Pg. 23
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to NRCS | UNAPPROVED | APPROVED | RELEASED | Comments
Meadow Springs Sewer Extension
| 55220 | 2019-04-17 |  | 2019-04-17 | 2019-05-23 | 2019-07-09
Greer Residence
2610 Greensboro Hwy | Tertiary | 2019-04-18 |  | 2019-04-18 |  | 2019-05-23 | 2019-05-28 | 2.80 acres
Jay Foster Residence
2950 Edge Water Drive | Tertiary | 2019-04-29 |  | 2019-04-29 |  | 2019-05-31 | 2019-06-03 | 1.20 acres
Highway 53 Retail
3161 Hog Mountain Road | 55606 | 2019-05-10 |  | 2019-05-10 | 2019-06-17
Hannay Residence
2402 Vintage Drive | Tertiary | 2019-03-12 |  | 2019-03-13 |  | 2019-03-26 | 2019-03-29 | .79 acres
Lot 1C Rambling Rill
2267 Rambling Rill Drive | Tertiary | 2019-02-22 |  | 2019-02-26 |  | 2019-03-07 | 2019-03-13 | .75 acres
Village at Stonebridge |  |  |  |  | 2019-08-29 | 2019-12-18
Stonebridge Pkwy | 11615 | 2019-07-18 |  | 2019-07-22 | 2019-10-28 | 2020-04-21 |  | 27.311 acres
Epps Bridge Centre - Outparcel #3
2045 Oconee Connector (Chipotle) | 13068 | 2019-07-26 |  | 2019-07-28 | 2019-09-03 |  |  | 1.2 acres
Village at Malcom Bridge
Lenru Road | 13695 | 2019-07-30 |  | 2019-07-31 |  |  |  | 10 acres
Tom Perdue
1230 Madison Court, Lot 31 | Tertiary | 2019-08-06 |  | 2019-08-06 | 2019-09-10 |  |  | .24 acres
Wildflower Meadows Amenity Lot
3120 Lily Lane | 16953 | 2019-08-09 |  | 2019-08-12 | 2019-09-16 | 2019-11-01 | 2019-11-05 | 2.70 acres
1170 Mars Hill Road
1170 Mars Hill Road | 20634 | 2019-08-26 |  | 2019-08-26 |  | 2019-12-09 | 2019-12-16
Stonewood Phase 2
1530 Union Church Road | 22540 | 2019-09-03 |  | 2019-09-04 | 2019-10-08 | 2019-12-02 | 2019-12-16 | 9.89 acres
Lot 31, Franklin Grove
1230 Madison Court | Tertiary | 2019-09-17 |  | 2019-09-18 |  |  |  | .24 acres
Grace Fellowship Church of God
1150 Malcom Bridge Road | 26342 | 2019-09-18 |  | 2019-09-18 | 2019-10-25 | 2019-12-04 | 2019-12-16 | 21.0 acres
Franklin Grove
2170 Franklin Grove Pkwy | Tertiary | 2019-09-18 |  | 2019-09-19 |  |  |  | .30 acres
Autumn Glen Phase 2
Rocky Branch Road | 27835 | 2019-09-24 |  | 2019-09-25 |  | 2019-12-30 |  | 15.3 acres
Autumn Glen Amenity Area
1569 Shagbark Way | 28832 | 2019-09-30 |  |  | 2019-11-07 |  |  | 1.4 acres
Kwon Medical | [5 empty] | 12/31/19 w/cond.
1975 Resurgence Drive | 29170 | 2019-09-30 |  |  | 2019-11-06 | 2020-02-12 |  | 2.10 acres
Prince Avenue Baptist Church
2131 Ruth Jackson Road | 29953 | 2019-10-03 |  | 2019-10-03 | 2019-11-07 | 2019-12-19 |  | 2.53 acres
Lot 1 Downs Creek Farms
1478 Downs Creek Drive | Tertiary | 2019-10-02 |  |  | 2019-11-13 | 2020-01-14 |  | .6 acres

## S.E. Log Pg. 24
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Winder | UNAPPROVED | APPROVED | RELEASED | Comments
Lot 2B Downs Creek Farms
1990 Downs Creek Drive | Tertiary | 2019-10-02 |  |  | 2019-11-13 |  |  | .8 acres
Lot 9 Meridian |  |  |  |  | 2020-01-09
1081 Cumberland Trail | Tertiary | 2019-10-02 |  | 2019-10-11 | 2019-11-14 | 2020-01-13 |  | .7 acres
Oconee Medical Office Building
1021 Barber Creek Drive | 36899 | 2019-10-29 |  | 2019-10-30 |  |  |  | 2.12 acres
Rodney Jones - Lot 22 Crystal Hills
1490 Crystal Hills Drive | Tertiary | 2019-11-11 |  | 2019-11-12 | 2019-12-16 | 2020-01-22 |  | .75 acres
Oconee County Animal Control Shelter Exp
1171 Branch Road | PSE20-0001 | 2020-01-16 |  | 2020-01-21 | 2020-02-12 | 2020-07-20 |  | .65 acres
Fairways CCRC Senior Community | [5 empty] | w/cond.
1900 Langford Drive | 59041 | 2020-01-27 |  | 2020-01-28 | 2020-02-26 | 2020-05-14 |  | 13.30 acres
Jones Petroleum Bogart Center
2430 Monroe Hwy | 60168 | 2020-01-27 |  | 2020-01-30 | 2020-03-03 |  |  | 34.00 acres
Charles Place | [5 empty] | w/cond.
Long Road | 62092 | 2020-02-05 |  | 2020-02-10 | 2020-03-13 | 2020-07-09 |  | 2.4 acres
Athens Academy Fieldhouse Improvements
1281 Spartan Ln | 65635 | 2020-02-20 |  | 2020-02-21 |  | 2020-04-01 |  | .58 acre
Elkabbani Residence
1414 Hillcrest Drive | 66423 | 2020-02-24 |  | 2020-02-26 |  | 2020-04-01 |  | 3.69 acres
Union Church Rd 12" Wtr Main Ext
1100 Union Chruch Rd |  | 2020-04-13 |  |  | 2020-05-08 |  |  | 2.28 acres
Jones Corner
2411 Hog Mountain Road | 87761 | 2020-05-21 | [5 empty] | 3.70 acres
American Pride Bank
1010 Pine Ridge Court |  | 2020-05-04 |  |  | 2020-06-09 | 2020-07-24 |  | 1.40 acres
Grace Fellowship Church of God
1150 Malcom Bridge Road | [5 empty] | 2020-06-12 |  | 22.80 acre
Research Quarter Commercial Subdivision
1180 Jennings Mill & Virgil Langford Road | 172168 | 2021-05-19 |  |  | 2020-06-22 | 2021-05-10 | 2021-05-19 | 25.76 acres
Willow Creek Subdivision
Block A | 90726 |  |  | 2020-05-07 |  | 2020-05-26 |  | 3.40 acres
Willow Creek Subdivision
Block F & G | 90726 |  |  | 2020-04-03 |  | 2020-05-04 |  | 3.40 acres
Resurgence Park Lot 5
1780 Resurgence Drive |  | 2020-07-10 |  | 2020-07-14 | 2020-07-28 | 2020-08-07 |  | 3.22 acres
Presbyterian Village Revisions |  |  |  |  | 2020-08-17
8021 Macon Hwy |  | 2020-07-27 |  |  | 2020-10-20 |  |  | 62.25 acres
Murrow Brothers
3361 Macon Hwy |  | 2020-09-03 |  | 2020-09-03 | 2020-09-17 | 2020-10-13 | 2020-10-15 | 2.97 acres
Wesley Phelps
1744 Edge Water Drive (Lot 16) |  | 2020-08-26 |  |  | 2020-10-07 | 2020-10-21 | 2020-11-03 | 1.50 acres
1171 Copperville Dr
1171 Copperville Dr |  | 2020-10-27 |  | 2020-11-28 | 2020-11-02 | 2020-11-18 |  | .38 acres
River's Edge Lot 35
2499 River's Edge Dr |  | 2020-11-02 |  | 2020-11-03 |  | 2020-11-09 |  | 1.18 acres

## S.E. Log Pg. 25
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Winder | UNAPPROVED | APPROVED | RELEASED | Comments
Resurgence Park Lot 5
1780 Resurgence Dive |  | 2020-07-10 |  | 2020-07-14 | 2020-07-28 | 2020-08-07 | 2020-08-17 | 3.22 acres
Presbyterian Village |  |  |  |  | 2021-02-02
8021 Macon Hwy |  | 2020-07-27 |  |  | 8/7-10/20/20 | 2021-02-09 |  | 62.25 acres
Murrow Brothers
3361 Macon Hwy |  | 2020-09-30 |  | 2020-09-03 | 2020-09-17 | 2020-10-13 | 2020-10-15 | 2.97 acres
Wesley Phelps
1744 Edge Water Drive (Lot 16) |  | 2020-08-26 |  |  | 2020-10-07 | 2020-10-21 | 2020-11-03 | 1.50 acres
1171 Copperville Drive
1171 Copperville Drive |  | 2020-10-27 |  | 2020-11-28 | 2020-11-02 | 2020-11-18 | 2020-12-29 | .38 acres
River's Edge Lot 35
2499 River's Edge Drive |  | 2020-11-02 |  | 2020-11-03 |  | 2020-11-09 | 2020-11-12 | 1.18 acres
Willow Creek Block F
Willow Creek Dr - Longleaf Ct |  | 2020-11-19 |  |  | 2020-12-15 | 2021-01-14 |  | 3.64 acres
Rhino Mini-Warehouse
Moreland Heights Drive | 136870 | 2020-12-18 |  | 2020-12-21 |  | 2021-01-26 |  | 4.7 acres
City Gate Office Park f.k.a.Summit Office Park | S.A.
Veterans Pkwy | 143563 | 2021-01-15 |  | 2021-01-19 | 2021-01-26 | 2021-02-23 |  | 1.88 acres
1302 Nellie Gray Court
1302 Nellie Gray Court | Tertiary | 2021-02-25 |  | 2021-03-01 |  | 2021-03-19 | 2021-03-25 | 1.52 acres
Jones Petroleum Bogart Retail Center | S.A. |  |  |  | 2021-07-26
2430 Monroe Hwy | 153428 | 2021-03-01 |  | 2021-03-02 | 2021-03-24 | 2021-08-23 |  | 16 acres
Costco at Epps Bridge Centre II | S.A. |  |  | Plans sent directly
Oconee Connector at Plaza Pkwy | 156921 | 2021-03-12 |  | to GSWCC | 2021-04-05 | 2021-04-20 |  | 14.1 acres
Lane Creek Plantation Phse 4 Lot 53
1000 Red Fox Trail | Tertiary | 2021-03-12 | [5 empty] | .72 acres
White Oak Farms | C.D. |  |  |  | 3/8-4/19
4900 Monroe Hwy | 157786 | 2021-03-11 |  |  | 6/7-7/12/21 |  |  | 24.69 acres
Mars Hill Mixed Use | C.D.
4060 Mars Hill Road |  | 2021-04-06 |  |  | 2021-04-30 |  |  | 16.07 acres
River Rock (F.K.A. Glacier Park) | C.D.
2321 & 2431 Moores Ford Road | 165116 | 2021-04-16 |  |  | 2021-05-05 | 2021-06-09 |  | 20.73 acres
The Tongia Residence
1599 Vintage Drive | Tertiary | 2021-04-19 |  | 2021-04-20 |  | 2021-05-03 |  | 2.06 acres
Schmidt Residence
2769 Rivers Edge Drive | Tertiary | 2021-04-29 |  | 2021-04-29 | 2021-05-24 |  |  | 1.8 acres
RAC Office Complex | S.A.
2891 Monroe Hwy | 173018 | 2021-05-21 |  | 2021-05-24 |  | 2021-06-21 |  | 2.05 acres
Resurgence Park Dental
1355 Resurgence Park | Tertiary | 2021-05-26 |  |  |  | 2021-06-17 |  | .91 acres
Daniells Bridge Road Tracts 1-3
1520 Daniells Bridge Road | Tertiary | 2021-05-26 | [5 empty] | 2.65 acres
Moreira Office
3475 Downs Creek Drive | Tertiary | 2021-05-27 |  |  | 2021-06-24 | 2021-06-29 |  | .0688 acres

## S.E. Log Pg 26
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Winder | UNAPPROVED | APPROVED | RELEASED | Comments
Celebration Athens
1220 & 1222 Dowdy Road | 172604 | 2021-05-20 |  | 2021-05-21 | 2021-06-16 | 2021-07-09 |  | 43.0 acres
Epps Bridge Centre I Outparcel 9 |  |  |  |  | 2021-09-20
1797 Oconee Connector |  |  |  |  | 2021-06-28 | 2021-10-07 | 2021-10-13 | .96 acres |  | Chipotle
Oconee Health Campus Phase VI | S.A.
1305 Jennings Mill Rd Bldg 400 | 180229 | 2021-06-23 | [5 empty] | 2.9 acres
Westland Subdivision
US Hwy 78 & Goat Farm Rd |  | 2021-06-24 |  | 2021-06-25 | 2021-07-22 | 2021-07-23 |  | 5.55 acres
Moreland Heights Assisted Living & Office
1052 Moreland Heights Rd |  | 2021-07-22 |  | 2021-07-26 | 2021-08-10 | 2021-09-14 |  | 8.02 acres
Malcom Bridge Estates
2241&2201 Malcom Bridge Road | 186188 | 2021-07-21 |  |  | 2021-08-10 | 2021-08-27 |  | 41.36 acres
Georgia Club Parcel C |  |  |  |  | 2021-09-27 | 2021-10-28
Georgia Club Drive |  |  |  |  | 2021-07-23 | 2021-10-27 |  | 7.64 acres
Spartan Estates Phase II
Spartan Lane |  |  |  |  | 2021-07-20 | 2021-08-16 |  | 9.75 acres
Hat Creek Burger Co
2045 Oconee Connector | Tertiary |  | 2021-07-06 |  | 2021-07-27 | 2021-10-05 | 2021-10-19 | 1.23 acres
Lane Creek Plantation Lot 59
1030 Holly Tree Court | Tertiary | 2021-08-10 |  | 2021-08-11 |  | 2021-08-27 |  | .72 acres
Prince Avenue Baptist Church Parking Lot
2131 Ruth Jackson Road | [5 empty] | 2021-08-19 | 2021-10-19 | 1.70 acres
Watkinsville Daycare
7575 Macon Hwy |  | 2021-08-24 |  | 2021-08-26 | 2021-09-15 | 2021-10-04 | 2021-11-08 | 1.52 acres
Westland Phase II |  |  |  | UPS Store
Goat Farm Rd & US Hwy 78-SR 10 | 192590 | 2021-08-30 |  | 2021-08-30 | 2021-09-21 | 2021-10-01 | 2021-10-06 | 48.0 acres
1050 Moss Creek
1050 Moss Creek Terrace | Tertiary | 2021-08-30 |  | 2021-08-31 |  |  | 2021-10-14 | .4 acres
1061 Moss Creek
1061 Moss Creek Drive | Tertiary | 2021-08-30 |  | 2021-08-31 |  |  | 2021-10-14 | .45 acres
Lindsey Residence
1471 Sikes Road | 195615 | 2021-09-13 |  |  |  | 2021-09-28 |  | .88 acres
New Middle School
7915 Hog Mountain Road | Exempt | 2021-09-20 |  | 2021-09-20 |  | 2021-10-04 |  | 23.70 acres
Westland Phase I |  |  |  | UPS Store
Hwy 78 & Goat Farm Rd | 200942 | 2021-10-01 |  | 2021-10-04 |  | 2021-10-18 | 2021-10-21 | 19.75 acres
Fred Gunter Site - Frontage Road
8120 Macon Hwy | 200427 | 2021-10-05 |  |  |  | 2021-10-21 |  | 8.37 acres
River Rock Phase II
2321 Moores Ford Rd | 202060 | 2021-10-14 |  | 2021-10-14 |  | 2021-10-21 | 2021-10-25 | 43.0 acres
Colony Square, Phse 3 - Lot 3
1071 Jamestown Blvd |  | 2021-10-01 |  | 2021-10-06 | 2021-10-14 | 2021-11-23 |  | 5.50 acres | Rec'd Plans from GSWCC on 12/9/2021
Lot 5 Resurgence Park
1780 Resurgence Park | Tertiary | 2021-11-08 |  | 2021-11-09 | 2021-12-01 | 2021-12-16 |  | 3.70 acres
Power Properties |  |  | Rec'd FedEx
1011 & 1021 Commerce Dr | 226667 | 2021-11-15 | Label 11/18/21 | 2021-11-19 |  |  |  | 1.87 acres
Ed Nash
1370 Old Bishop Road | Tertiary | 2021-11-22 |  |  |  | 2021-12-03 | 2021-12-08 | .76 acres
Stonewood Phase 3
1530 Union Church Rd | 211202 | 2021-11-24 |  |  | 2021-12-14 | 2022-01-07 |  | 6.21 acres

## S.E. Log Pg. 27
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Winder | UNAPPROVED | APPROVED | RELEASED | Comments | Approved Plans Rec'd from GSWCC
Hamby Residence
1830 Old Oak Lane | Tertiary | 2021-11-30 |  | 2021-12-01 |  | 2021-12-13 | 2022-01-05 | .93 acres
Lane Creek Lot 9 Block E
1090 Riverhill Dr | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-30 | 2022-01-05 | .50 acres
Lane Creek Lot 11 Block E
1110 Riverhill Dr | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-27 | 2022-01-05 | .50 acres
Lane Creek Lot 13 Block E
1130 Riverhill Dr | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-30 | 2022-01-05 | .50 acres
Lane Creek Lot 47 Block D
1191 Red Fox Trail | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-27 | 2022-01-05 | .50 acres
Lane Creek Lot 51 Block D
1151 Red Fox Trail | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-30 | 2022-01-05 | .50 acres
Lane Creek Lot 52 Block D
1131 Red Fox Trail | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-30 | 2022-01-05 | .50 acres
Lane Creek Lot 61 Block D
1041 Holly Tree Ct | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-30 | 2022-01-05 | .50 acres
Lane Creek Lot 62 Block D
1051 Holly Tree Ct | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-27 | 2022-01-05 | .50 acres
Lane Creek Lot 65 Block D
1150 Red Fox Trail | Tertiary | 2021-12-13 |  | 2021-12-14 |  | 2021-12-30 | 2022-01-05 | .50 acres
Jimmy Daniel Office Park
1110 & 1130 Jimmy Daniel Rd | 221926 | 2021-12-17 |  | 2021-12-21 |  | 2021-12-27 | 2022-01-19 | 14.47 acres
CEC Mars Hill Road |  |  |  |  | 2022-02-28
1010 Commerce Dr |  | 2021-12-21 |  | 2021-12-22 | 2022-01-05 | 2022-03-03 |  | 4.178 acres |  | Fees ?
Precision Landscape Management
1110 Commerce Drive |  | 2022-01-26 |  | 2022-01-26 |  | 2022-02-14 |  | 4.20 acres
Univeristy Cancer and Blood Center
1460 Resurgence Dr | Teritary | 2022-02-21 |  | 2022-02-23 |  | 2022-02-25 |  | 4.46 acres |  | NOI?
Jordan Drive Office Complex
1961 Epps Bridge Pkwy | 230627 | 2022-02-24 |  | 2022-02-25 |  |  |  | 1.4 acres
Oconee County Administrative Building |  |  |  | 5/16 @2nd) | 2022-03-03 | 2022-05-12
7635 Macon Hwy |  | 2022-02-25 |  | 2022-02-25 | 2022-04-04 | w/cond. |  | 8.5 acres
Lenhardt Residence
1252 Rivers Edge Dr | Tertiary | 2022-03-09 |  | 2022-03-10 | 2022-03-15 | 2022-03-25 |  | .99 acres
Daniells Bridge Pump Station & Force Main Upgrade
1621 Daniells Bridge Road | [5 empty] | 2022-03-18 |  | 4.90 acres
Ulm Residence
2310 Cole Springs Drive | Tertiary | 2022-03-25 |  |  |  | 2022-04-06 |  | .99 acres
Grace Fellowship
1150 Malcom Bridge Road |  | 2022-03-25 | [5 empty] | 20.0 acres |  | Pd NOI Owe Soil Erosion
Edwards Residence
2880 Spartan Estates Drive | Tertiary | 2022-03-28 |  |  |  | 2022-04-06 | 2022-04-15 | .63 acres
Ahmed Residence
1721 Vintage Drive | Tertiary | 2022-03-30 |  |  |  | 2022-04-08 | 2022-04-15 | .75 acres
Hammond Residence
2402 Downs Creek Drive | Tertiary | 2022-04-01 |  |  |  | 2022-04-14 | 1913-03-07 | 1.39 acres
UNG Oconee Parking Lot Improvements |  |  |  | 5/16 (2nd)
1201 Bishop Farms Pkwy |  | 2022-04-22 | [5 empty] | 3.70 acres
Stonewood Amenity (Stonewood Phse I)
1225 Stone Road | Tertiary | 2022-05-03 |  |  | 2022-05-12 | 2022-06-10 | 2022-06-16 | 1.73 acres

## S.E. Log Pg. 28
| NUMBER | DATE REC'D | RET'D TO DEV | FedEx to Winder | UNAPPROVED | APPROVED | RELEASED | Comments | Approved Plans Rec'd from GSWCC
Westland Primary Amenity Area
1461 Goat Farm Rd | 247633 | 2022-05-11 |  | 2022-05-11 |  | 2022-05-18 |  | 3.20 acres
Four Seasons Carwash
Mars Hill Road (C-2-53) |  | 2022-05-13 |  |  | 2022-05-26 | 2022-06-02 | 2022-06-15 | 5.04 acres
Lakewood Park Amenity Area
Barber Creek Road | 248479 | 2022-05-16 |  | 2022-05-17 | 2022-05-26 | 2022-05-31 | 2022-06-15 | 5.48 acres
Malcom Bridge Estates Primary Amenity
2241 Malcom Bridge Road | 249246 | 2022-05-20 |  | 2022-05-20 | 2022-06-01 | 2022-07-14 | 2022-07-18 | .67 acres | 2022-07-18
Belfair Phase 2 Lot 31C
1120 Pearl Way | Tertiary | 2022-05-24 |  | 2022-05-27 |  | 2022-06-07 |  | .80 acres |  | emailed Matt Sullins to pick up plan 6/15/2022
Meriweather Drive (SFD)
1540 Meriweather Drive | 252921 | 2022-06-07 |  | 2022-06-07 |  | 2022-06-14 |  | .32 acres
1540 Meriweather Drive
Latham Drive (SFD)
1290 Latham Drive | 254246 | 2022-06-14 |  | 2022-06-15 |  | 2022-07-05 |  | .49 acres
Athens Academy Tennis Courts
1281 Spartan Lane | 254888 | 2022-06-16 |  | 2022-06-17 | 2022-06-28 |  |  | .92 acres
Robinson Creek
2361 New High Shoals Road | 258414 | 2022-07-05 |  | 2022-07-06 |  | 2022-07-25 |  | 8.10 acres
Porter Creek
3028 Barnett Shoals Rd | 262581 | 2022-07-22 |  | 2022-07-22 | 2022-07-28 | 2022-08-09 |  | 1.64 acres |  | pd soil erosion fee - owe for NOI fee's
Life Church of Athens
1128 Summit Grove Drive | 265622 | 2022-08-08 |  |  | 2022-08-11 | 2023-02-01 |  |  |  | pd soil erosion fee - owe for NOI fee's
Jim 'n Nicks
1787 Oconee Connector | Tertiary | 2022-08-12 |  |  |  | 2022-08-30 |  | 1.07 acres |  | Need NOI Paperwork
Phase II River Rock (F.K.A. Glacier Park)
2321 & 2431 Moores Ford Rd | Tertiary |  |  |  |  | 2022-08-11 |  | 41.62 acres |  | Plans did not come through CE until Approved
Georgia Arch Partners LLC
1070 Windridge Drive |  | 2022-08-23 |  | 2022-08-24 |  | 2022-09-01 | 2022-09-14 | .6 acres |  | Within 200' of State Waters
Magnolia Estates Assisted Living
1641 Virgil Langford Rd |  | 2022-10-21 |  |  |  | 2022-11-10 |  | 14.90 acres
Bell Lake Estates
Colham Ferry Rd (B-7-41) |  | 2022-10-21 |  |  | 2022-11-17 | 2023-01-06 |  | 23.40 acres |  | contaced Frank on 1/18 will release plans when proof of EPD NOI received
Tennis Amenity Area Westland MPD
1461 Goat Farm Road | 289121 | 2022-11-28 |  | 2022-11-29 |  |  |  | 3.0 acres
MBES Addition
2500 Malcom Bridge Road | 293722 | 2022-12-22 |  | 2022-12-27 |  | 2023-01-12 |  | 2.02 acres |  | emailed J Moon on 1/18 will release plans when proof of EPD NOI received
Mutty Paws
1050-1060 Talus Street |  | 2023-01-12 |  | 2023-01-13 |  |  |  | 1.90 acres |  | need soil erosion & NOI fees
The Summit at Talus
1041-1061 Talus Street | 298124 | 2023-01-13 |  |  | 2023-02-01 |  |  |  |  | need NOI fees
Swope Residence |  | 2023-02-08 |  | 2023-02-09
Hodges Mill Road | 299664 | 2023-01-20 |  | 2023-01-23 |  |  |  | 8.94 acres |  | need NOI fees
Resurgence Park Medical Offices
1715 Resurgence Drive | 302677 | 2023-02-03 |  | 2023-02-06 |  | 2023-02-10 |  | 2.3 acres
Layson Residence
2368 Barnett Shoals Road |  | 2023-02-07 |  | 2023-02-08 |  |  |  | 2.47 acres |  | need Soil Erosion & NOI fees